## Software_Procurement_Approval_(
Task ID | Created At | Completed At | Last Modified | Name | Section/Column | Assignee | Assignee Email | Start Date | Due Date | Tags | Notes | Projects | Parent task | Blocked By (Dependencies) | Blocking (Dependencies) | Path | Team Member
1211448248895778 | 2025-09-23 |  | 2025-09-23 | Start here! |  |  |  |  | 2025-09-24 |  | Your request has been reviewed by a member of the Exec team, and it has been determined that your request needs to go through an RFI or RFP process. What is a Request for Information (RFI)? Scenario: I have a need but I don't know what software options there are An RFI gathers information about potential vendors and their capabilities. Some RFIs mature into RFPs. Document used by organizations to gather information about potential vendors, products, or services before making a purchasing decision. It’s typically issued in the early stages of a project when the organization needs to understand the options available in the market and gain insight into vendor capabilities, offerings, and solutions. What is a Request for Proposal (RFP)? Scenarios: I want to explore a few options There are numerous competitors offering similar software services, with little differentiation between them; as a result, cost becomes the primary factor in decision-making. An RFP (Request for Proposal) is a formal document issued by an organization to solicit proposals from vendors or service providers. It outlines the organization's specific needs, objectives, and requirements for a particular project or service, and invites vendors to submit detailed proposals on how they can meet those needs. The RFP typically includes information such as the scope of work, budget, timeline, and evaluation criteria, and vendors respond with a proposal that explains their approach, qualifications, costs, and timeline for completing the project. The organization then reviews the proposals and selects the vendor that best meets its criteria. From an Asana perspective, you would follow the same predictive task path to acquire software. All of the tasks under this software request have been identified for you. Let's start by having you complete the subtasks in this task. Please review the tasks and the due dates. Move tasks to different dates as needed. Most of the tasks rely on the completion of previous tasks. In those cases, dates will recalculate to accommodate your date change(s). IMPORTANT NOTE: The 'select one solution to test' task is not reliant on a task dependency. Please make sure to update that specific task if you make changes to previous tasks before that one. Copy the templates from https://drive.google.com/drive/folders/1IiqeBA5I3sITywwXlQYGOjM9xxg73KiI?usp=drive_link to the Organization's Software Procurement folder. These documents are to be used at various points during the implementation and will help close out your processes. |  | test
1211448250359659 | 2025-09-23 |  | 2025-09-23 | Review tasks and due dates |  |  |  |  | 2025-09-24 |  | Review the auto populated dates and modify based on your timeline. |  | Start here! |  | Copy templates
1211448250359666 | 2025-09-23 |  | 2025-09-23 | Copy templates |  |  |  |  | 2025-09-24 |  |  |  | Start here! | Review tasks and due dates
1211448250287237 | 2025-09-23 |  | 2025-09-23 | Align Director's schedules for 1:1 meetings |  |  |  |  | 2025-10-12 |  | Initiating a software request requires you to collaborate with all of the CITE subteam Directors to assess the impact on their teams. Align their schedules with yours to arrange Discovery meetings. |  | test |  | Email individual meeting invites to each Director
1211448250287244 | 2025-09-23 |  | 2025-09-23 | Email individual meeting invites to each Director |  |  |  |  | 2025-10-13 |  | Please use the Communication template that you copied in the first task. Find the 'Communication for Directors Invite' section. There are two scenarios in the template. Scenario 1 is a meeting invite to share the software you have in mind and get feedback from the Director(s). Scenario 2 is a meeting with the Director(s) to gather requirements from their team. |  | test | Align Director's schedules for 1:1 meetings | Meet with each Director and their team members
1211448250287251 | 2025-09-23 |  | 2025-09-23 | Meet with each Director and their team members |  |  |  | 2025-10-15 | 2025-10-29 |  | These sessions are meant to enhance transparency between teams and also make sure we account for everyone's input during this stage of the selection process. At this stage, we want to gather their requirements and gauge their interest in being involved in the process. It is important to emphasize the significance of reviewing tasks, meeting deadlines, and actively participating in the process. Additionally, we want to inform Directors that all communications regarding the project will be posted here, in Asana, with assignees and deadlines. The following questions are part of the invite sent to Directors and what you will be asking each subteam to respond to: If software is known: Are you currently using any software similar to the one we are considering? If so, which software, and how are you utilizing it? Would your team be interested in using this software? If so, for what specific purposes? How would you use the solution? Are there any data or features from the solution that you believe would be beneficial for your team to access? If software is to be selected from a list of vendors: Are you currently using any software similar to the solution we are considering? If so, which software, and how are you using it? How would you use the solution? How does considering this software impact your operations? Do you see your team as potential users of this new software solution? After reviewing our requirements, are there any additional requirements you would like to include as we search for a solution? Are there specific data types or features that you believe would be valuable for your team to have access to? |  | test | Email individual meeting invites to each Director | Conduct Exec team impact assessment and requirements gathering meeting,Conduct Ed Team impact assessment and requirements gatheringn meeting,Conduct Resource and Programs impact assessment and requirements gathering meeting,Conduct Marketing impact assessment and requirements gathering meeting,Document requirements from Director meetings to the Criteria Matrix
1211448250359688 | 2025-09-23 |  | 2025-09-23 | Conduct Exec team impact assessment and requirements gathering meeting |  |  |  |  | 2025-10-16 |  |  |  | Meet with each Director and their team members | Meet with each Director and their team members
1211448250388150 | 2025-09-23 |  | 2025-09-23 | Conduct Ed Team impact assessment and requirements gatheringn meeting |  |  |  |  | 2025-10-18 |  |  |  | Meet with each Director and their team members | Meet with each Director and their team members
1211448250388157 | 2025-09-23 |  | 2025-09-23 | Conduct Resource and Programs impact assessment and requirements gathering meeting |  |  |  |  | 2025-09-23 |  |  |  | Meet with each Director and their team members | Meet with each Director and their team members
1211448250388164 | 2025-09-23 |  | 2025-09-23 | Conduct Marketing impact assessment and requirements gathering meeting |  |  |  |  | 2025-10-19 |  |  |  | Meet with each Director and their team members | Meet with each Director and their team members
1211448250287258 | 2025-09-23 |  | 2025-09-23 | Document requirements from Director meetings to the Criteria Matrix |  |  |  | 2025-10-15 | 2025-10-29 |  | After meeting with each Director and the team members they invite, please add any additional criteria you've gathered into the Criteria Matrix Template located in the templates folder. If you know the software you want, it must meet the list of CITE criteria as well as the criteria that you and the Directors have identified as requirements. |  | test | Meet with each Director and their team members | Email Criteria Matrix to Directors (or team leads) for feedback,Finalize the criteria matrix template
1211448310041519 | 2025-09-23 |  | 2025-09-23 | Email Criteria Matrix to Directors (or team leads) for feedback |  |  |  |  | 2025-10-30 |  | Locate the Communications template document you copied earlier. Find the Criteria Email to Director or Team Lead language and use it as a starting point. Send an email communication to the Directors to ensure that their requirements have been considered in the Criteria Matrix, which will be sent to vendors for their response. |  | test | Document requirements from Director meetings to the Criteria Matrix
1211448310174781 | 2025-09-23 |  | 2025-09-23 | Finalize the criteria matrix template |  |  |  |  | 2025-10-31 |  | After receiving feedback from Directors and/or team leads, finalize the Criteria Matrix before sharing it with potential vendors. If you know the software you want, ensure that it meets all of the must-have requirements in the Criteria Matrix. |  | test | Document requirements from Director meetings to the Criteria Matrix | Email your Sponsor with an update
1211448310174788 | 2025-09-23 |  | 2025-09-23 | Email your Sponsor with an update |  |  |  |  | 2025-11-02 |  | If you have a sponsor for this request, please send them an email with an update. Locate the Communications template document and use the Initial Sponsor Communication template as a starting point. |  | test | Finalize the criteria matrix template | Select 3-4 vendor platforms to do a quick vendor discovery
1211448310174795 | 2025-09-23 |  | 2025-09-23 | Select 3-4 vendor platforms to do a quick vendor discovery |  |  |  |  | 2025-11-04 |  | ** This task only applies if you are considering multiple software solutions and do not have one in mind, and you are looking for software that best meets your requirements. If you are looking to integrate data with Novi AMS, start by finding https://www.noviams.com/third-party-integrations. If vendor(s) are listed on their website, chances are they have a good relationship with Novi. To do further research on vendors, check out vendor Capterra reviews. |  | test | Email your Sponsor with an update | Participate in vendor discovery calls,Email the project team to invite them to discovery sessions
1211448310174802 | 2025-09-23 |  | 2025-09-23 | Email the project team to invite them to discovery sessions |  |  |  |  | 2025-11-06 |  | ** This task only applies if you are considering multiple software solutions and do not have one in mind, and you are looking for software that best meets your requirements. Please utilize the Communication template that you copied in the first task. Locate the Invite to Demos language and use it as a starting point. Invite any Directors, team leads, or Sponsors who wish to participate in the demos. |  | test | Select 3-4 vendor platforms to do a quick vendor discovery
1211448250058578 | 2025-09-23 |  | 2025-09-23 | Participate in vendor discovery calls |  |  |  | 2025-11-06 | 2025-11-12 |  |  |  | test | Select 3-4 vendor platforms to do a quick vendor discovery | Email vendors from Discovery you want to invite to RFI/RFP
1211448250058585 | 2025-09-23 |  | 2025-09-23 | Email vendors from Discovery you want to invite to RFI/RFP |  |  |  | 2025-11-07 | 2025-11-12 |  | ** This task only applies if you are considering multiple software solutions and do not have one in mind, and you are looking for software that best meets your requirements. Complete vendor demo forms, set up 60-minute demos, and obtain pricing. Record one-time pricing and ongoing costs in the Criteria matrix. RFI: Complete matrix and provide dates/times for extended 1 hour demo RFP: Copy https://citeorg-my.sharepoint.com/:w:/r/personal/laurel_nava_cite_org/Documents/Microsoft%20Teams%20Chat%20Files/CITE%20RFP%20Template.docx?d=w9bc13ef4ffb94d1a8244c25abd471fb0&csf=1&web=1&e=fjJJ0h, modify the copy, convert to PDF, save PDF in Google Drive, share RFP proposal you create using the template. Have vendor complete matrix and provide dates/times for extended 1 hour demo. |  | test | Participate in vendor discovery calls | Wait for vendor responses
1211448250058592 | 2025-09-23 |  | 2025-09-23 | Wait for vendor responses |  |  |  | 2025-11-13 | 2025-12-08 |  | ** This task only applies if you are considering multiple software solutions and do not have one in mind, and you are looking for software that best meets your requirements. This is a waiting period while we wait for responses from vendors. |  | test | Email vendors from Discovery you want to invite to RFI/RFP
1211448250058599 | 2025-09-23 |  | 2025-09-23 | Create a Criteria Matrix rubric for each vendor presentation and share with project team members |  |  |  |  | 2025-12-09 |  | ** This task only applies if you are considering multiple software solutions and do not have one in mind, and you are looking for software that best meets your requirements. Make a copy of the criteria matrix and create a tab for each vendor on your Criteria Matrix sheet. |  | test |  | Get platform selection buy-in from other teams
1211448250674270 | 2025-09-23 |  | 2025-09-23 | Participate in demos |  |  |  | 2025-12-21 | 2026-01-01 |  | ** This task only applies if you are considering multiple software solutions and do not have one in mind, and you are looking for software that best meets your requirements. Review matrix responses from Directors and project team members Send Directors and team members an email with matrix scores Inivite Directors and team members. As you meet with vendors during demos and share information about their platforms, evaluate the platforms using the criteria matrix. For each measurable criterion, score the platforms using the following scores: 4 - Meets requirement 3 - Almost meets requirement 2 - Somewhat meets requirement 1 - Does not meet requirement |  | test
1211448250674292 | 2025-09-23 |  | 2025-09-23 | Get platform selection buy-in from other teams |  |  |  | 2026-01-02 | 2026-01-21 |  | The purpose of this task is to reiterate requirements, let everyone know about demos coming up, and encourage them to participate in the upcoming demos. |  | test | Create a Criteria Matrix rubric for each vendor presentation and share with project team members
1211448250715656 | 2025-09-23 |  | 2025-09-23 | Review matrix responses from Directors and project team members |  |  |  | 2026-01-02 | 2026-01-11 |  |  |  | Get platform selection buy-in from other teams
1211448250715663 | 2025-09-23 |  | 2025-09-23 | Send Directors and team members an email with matrix scores |  |  |  | 2026-01-11 | 2026-01-21 |  |  |  | Get platform selection buy-in from other teams
1211448484003652 | 2025-09-23 |  | 2025-09-23 | NOTE: Update the due date on this task! Email all vendors for thank them for their participation. Email one vendor to request a sandbox environment. |  |  |  |  | 2026-01-22 |  | The purpose of this task is to communicate the status of all vendors after the demos. For the one that is selected, ask for 2 references you can contact. |  | test |  | Test your requirements in Sandbox environment
1211448484084414 | 2025-09-23 |  | 2025-09-23 | Send rejections |  |  |  |  | 2026-01-22 |  | Thank the participants and inform them that we will not be moving forward. Please refer to the communication plan. |  | NOTE: Update the due date on this task! Email all vendors for thank them for their participation. Email one vendor to request a sandbox environment.
1211448484084421 | 2025-09-23 |  | 2025-09-23 | Send request for a sandbox |  |  |  |  | 2026-01-22 |  | Please send an email to request information from those under consideration. Refer to the communication plan. |  | NOTE: Update the due date on this task! Email all vendors for thank them for their participation. Email one vendor to request a sandbox environment.
1211448484003659 | 2025-09-23 |  | 2025-09-23 | Contact Vendor References and start chat with Marketing about integrations |  |  |  | 2026-01-23 | 2026-02-02 |  | At this stage, contact the vendor's references. Refer to the the Reference Check Questions sheet in Google Drive. |  | test
1211448484003666 | 2025-09-23 |  | 2025-09-23 | Test your requirements in Sandbox environment |  |  |  | 2026-01-21 | 2026-02-10 |  | At this point, you have access to the sandbox environment. Please take the criteria list you created and test the functionality based on what you noted as "must-haves" and "nice-to-haves." This is a critical milestone. To move forward with the vendor, you must get buy-in from all of your stakeholders by the due date. |  | test | NOTE: Update the due date on this task! Email all vendors for thank them for their participation. Email one vendor to request a sandbox environment. | Review Contract for language
1211448484084433 | 2025-09-23 |  | 2025-09-23 | Send Directors and team members an email to participate in sandbox testing along with credentials |  |  |  | 2026-01-21 | 2026-02-10 |  |  |  | Test your requirements in Sandbox environment
1211448484154875 | 2025-09-23 |  | 2025-09-23 | Get final buy in or halt direction from Directors and team members |  |  |  | 2026-02-10 | 2026-02-20 |  | Please tag your stakeholders on this task and have them respond in the comments with either "Proceed" or "Halt." |  | Test your requirements in Sandbox environment
1211448484003673 | 2025-09-23 |  | 2025-09-23 | Review Contract for language |  |  |  | 2026-02-03 | 2026-02-15 |  | The purpose of this task is to ensure CITE is protected, CITE owns data, and that we are meeting state and federal regulations. Task is to be assigned to Andrea when this process goes for draft approval. |  | test | Test your requirements in Sandbox environment | Contract review period
1211448484084407 | 2025-09-23 |  | 2025-09-23 | Contract review period |  |  |  | 2026-01-01 | 2026-01-16 |  | Two week period for Andrea to review Contract language. |  | test | Review Contract for language
1211448250439814 | 2025-09-23 |  | 2025-09-23 | Email progress with Sponsor |  |  |  |  | 2026-02-17 |  | Share progress with the software selection. |  | test |  | Training with vendor
1211448250984750 | 2025-09-23 |  | 2025-09-23 | Training with vendor |  |  |  | 2026-02-18 | 2026-03-02 |  |  |  | test | Email progress with Sponsor | Implement selected software
1211448250984757 | 2025-09-23 |  | 2025-09-23 | Implement selected software |  |  |  | 2026-03-22 | 2026-04-11 |  | Period when we work with the vendor to implement software. |  | test | Training with vendor | Test your requirements in live environment
1211448251031212 | 2025-09-23 |  | 2025-09-23 | Migrate |  |  |  | 2026-02-17 | 2026-03-22 |  |  |  | Implement selected software
1211448251031219 | 2025-09-23 |  | 2025-09-23 | Integrate |  |  |  | 2026-02-17 | 2026-03-22 |  |  |  | Implement selected software
1211448250984764 | 2025-09-23 |  | 2025-09-23 | Test your requirements in live environment |  |  |  | 2026-04-11 | 2026-04-21 |  | Final criteria matrix test to ensure that the platform meets all requirements from all teams. |  | test | Implement selected software | Record and report software issues
1211448250984771 | 2025-09-23 |  | 2025-09-23 | Record and report software issues |  |  |  | 2026-04-11 | 2026-05-01 |  | Please go to the templates folder and find the, 'Record Changes or Issues' File. Record any issues and changes that you would like the vendor to make. |  | test | Test your requirements in live environment | Work with vendor to address issues
1211448482271267 | 2025-09-23 |  | 2025-09-23 | Work with vendor to address issues |  |  |  | 2026-04-11 | 2026-05-11 |  | Time the for vendor has to address issues. As defects or changes are addressed, update the, 'Record Change or Issues' file with updates. |  | test | Record and report software issues | Share new software news on Staff channel,Perform a Retrospective exercise
1211448482271274 | 2025-09-23 |  | 2025-09-23 | Share new software news on Staff channel |  |  |  |  | 2026-05-12 |  | Sharing news with other staff members for visibility and potential collaboration. |  | test | Work with vendor to address issues | Update CITE Software Excel spreadsheet
1211448482271281 | 2025-09-23 |  | 2025-09-23 | Update CITE Software Excel spreadsheet |  |  |  |  | 2026-05-13 |  | CITE maintains a single software sheet where we record all software requests. The purpose is to keep track of all the different software solutions selected, estimated costs, actual Total Cost of Ownership (TCO), status and for what year (Sokie). Location: https://citeorg.sharepoint.com/:x:/r/sites/Staff269/Shared%20Documents/Operational/Software%20Inventory.xlsx?d=w9a2dc28546374acb9858374ed0e59c39&csf=1&web=1&e=4DSrhy |  | test | Share new software news on Staff channel
1211448484450466 | 2025-09-23 |  | 2025-09-23 | Perform a Retrospective exercise |  |  |  |  | 2026-05-14 |  | The purpose of a retrospective is to look back at all of our work to see: what we did well, what we can improve, what we can get rid of, and what we can try in the future. Find the Retrospective file in the templates folder. After retrospective is complete, review notes and make improvements to the process in Asana or the original template files in https://drive.google.com/drive/folders/1IiqeBA5I3sITywwXlQYGOjM9xxg73KiI?usp=drive_link. |  | test | Work with vendor to address issues
1211448484513370 | 2025-09-23 |  | 2025-09-23 | Perform Impact Analysis |  |  |  |  | 2026-03-24 |  |  |  | Perform a Retrospective exercise
1211448379404407 | 2025-09-23 |  | 2025-09-23 | test2 | RFI/RFP Path | [6 empty] | Software Procurement Approval (SPA) Process |  |  |  | Project Path
1211448482894701 | 2025-09-23 |  | 2025-09-23 | Start here! |  |  |  |  | 2025-09-24 |  | Your request has been reviewed by a member of the Exec team, and it has been determined that your request needs to go through an RFI or RFP process. What is a Request for Information (RFI)? Scenario: I have a need but I don't know what software options there are An RFI gathers information about potential vendors and their capabilities. Some RFIs mature into RFPs. Document used by organizations to gather information about potential vendors, products, or services before making a purchasing decision. It’s typically issued in the early stages of a project when the organization needs to understand the options available in the market and gain insight into vendor capabilities, offerings, and solutions. What is a Request for Proposal (RFP)? Scenarios: I want to explore a few options There are numerous competitors offering similar software services, with little differentiation between them; as a result, cost becomes the primary factor in decision-making. An RFP (Request for Proposal) is a formal document issued by an organization to solicit proposals from vendors or service providers. It outlines the organization's specific needs, objectives, and requirements for a particular project or service, and invites vendors to submit detailed proposals on how they can meet those needs. The RFP typically includes information such as the scope of work, budget, timeline, and evaluation criteria, and vendors respond with a proposal that explains their approach, qualifications, costs, and timeline for completing the project. The organization then reviews the proposals and selects the vendor that best meets its criteria. From an Asana perspective, you would follow the same predictive task path to acquire software. All of the tasks under this software request have been identified for you. Let's start by having you complete the subtasks in this task. Please review the tasks and the due dates. Move tasks to different dates as needed. Most of the tasks rely on the completion of previous tasks. In those cases, dates will recalculate to accommodate your date change(s). IMPORTANT NOTE: The 'select one solution to test' task is not reliant on a task dependency. Please make sure to update that specific task if you make changes to previous tasks before that one. Copy the templates from https://drive.google.com/drive/folders/1IiqeBA5I3sITywwXlQYGOjM9xxg73KiI?usp=drive_link to the Organization's Software Procurement folder. These documents are to be used at various points during the implementation and will help close out your processes. |  | test2
1211448483597973 | 2025-09-23 |  | 2025-09-23 | Review tasks and due dates |  |  |  |  | 2025-09-24 |  | Review the auto populated dates and modify based on your timeline. |  | Start here! |  | Copy templates
1211448483597980 | 2025-09-23 |  | 2025-09-23 | Copy templates |  |  |  |  | 2025-09-24 |  |  |  | Start here! | Review tasks and due dates
1211448482894708 | 2025-09-23 |  | 2025-09-23 | Align Director's schedules for 1:1 meetings |  |  |  |  | 2025-10-12 |  | Initiating a software request requires you to collaborate with all of the CITE subteam Directors to assess the impact on their teams. Align their schedules with yours to arrange Discovery meetings. |  | test2 |  | Email individual meeting invites to each Director
1211448483597952 | 2025-09-23 |  | 2025-09-23 | Email individual meeting invites to each Director |  |  |  |  | 2025-10-13 |  | Please use the Communication template that you copied in the first task. Find the 'Communication for Directors Invite' section. There are two scenarios in the template. Scenario 1 is a meeting invite to share the software you have in mind and get feedback from the Director(s). Scenario 2 is a meeting with the Director(s) to gather requirements from their team. |  | test2 | Align Director's schedules for 1:1 meetings | Meet with each Director and their team members
1211448483597959 | 2025-09-23 |  | 2025-09-23 | Meet with each Director and their team members |  |  |  | 2025-10-15 | 2025-10-29 |  | These sessions are meant to enhance transparency between teams and also make sure we account for everyone's input during this stage of the selection process. At this stage, we want to gather their requirements and gauge their interest in being involved in the process. It is important to emphasize the significance of reviewing tasks, meeting deadlines, and actively participating in the process. Additionally, we want to inform Directors that all communications regarding the project will be posted here, in Asana, with assignees and deadlines. The following questions are part of the invite sent to Directors and what you will be asking each subteam to respond to: If software is known: Are you currently using any software similar to the one we are considering? If so, which software, and how are you utilizing it? Would your team be interested in using this software? If so, for what specific purposes? How would you use the solution? Are there any data or features from the solution that you believe would be beneficial for your team to access? If software is to be selected from a list of vendors: Are you currently using any software similar to the solution we are considering? If so, which software, and how are you using it? How would you use the solution? How does considering this software impact your operations? Do you see your team as potential users of this new software solution? After reviewing our requirements, are there any additional requirements you would like to include as we search for a solution? Are there specific data types or features that you believe would be valuable for your team to have access to? |  | test2 | Email individual meeting invites to each Director | Conduct Exec team impact assessment and requirements gathering meeting,Conduct Ed Team impact assessment and requirements gatheringn meeting,Conduct Resource and Programs impact assessment and requirements gathering meeting,Conduct Marketing impact assessment and requirements gathering meeting,Document requirements from Director meetings to the Criteria Matrix
1211448483184485 | 2025-09-23 |  | 2025-09-23 | Conduct Exec team impact assessment and requirements gathering meeting |  |  |  |  | 2025-10-16 |  |  |  | Meet with each Director and their team members | Meet with each Director and their team members
1211448483184492 | 2025-09-23 |  | 2025-09-23 | Conduct Ed Team impact assessment and requirements gatheringn meeting |  |  |  |  | 2025-10-18 |  |  |  | Meet with each Director and their team members | Meet with each Director and their team members
1211448483184499 | 2025-09-23 |  | 2025-09-23 | Conduct Resource and Programs impact assessment and requirements gathering meeting |  |  |  |  | 2025-09-23 |  |  |  | Meet with each Director and their team members | Meet with each Director and their team members
1211448483806914 | 2025-09-23 |  | 2025-09-23 | Conduct Marketing impact assessment and requirements gathering meeting |  |  |  |  | 2025-10-19 |  |  |  | Meet with each Director and their team members | Meet with each Director and their team members
1211448483597966 | 2025-09-23 |  | 2025-09-23 | Document requirements from Director meetings to the Criteria Matrix |  |  |  | 2025-10-15 | 2025-10-29 |  | After meeting with each Director and the team members they invite, please add any additional criteria you've gathered into the Criteria Matrix Template located in the templates folder. If you know the software you want, it must meet the list of CITE criteria as well as the criteria that you and the Directors have identified as requirements. |  | test2 | Meet with each Director and their team members | Email Criteria Matrix to Directors (or team leads) for feedback,Finalize the criteria matrix template
1211448483833082 | 2025-09-23 |  | 2025-09-23 | Email Criteria Matrix to Directors (or team leads) for feedback |  |  |  |  | 2025-10-30 |  | Locate the Communications template document you copied earlier. Find the Criteria Email to Director or Team Lead language and use it as a starting point. Send an email communication to the Directors to ensure that their requirements have been considered in the Criteria Matrix, which will be sent to vendors for their response. |  | test2 | Document requirements from Director meetings to the Criteria Matrix
1211448483833089 | 2025-09-23 |  | 2025-09-23 | Finalize the criteria matrix template |  |  |  |  | 2025-10-31 |  | After receiving feedback from Directors and/or team leads, finalize the Criteria Matrix before sharing it with potential vendors. If you know the software you want, ensure that it meets all of the must-have requirements in the Criteria Matrix. |  | test2 | Document requirements from Director meetings to the Criteria Matrix | Email your Sponsor with an update
1211448483833096 | 2025-09-23 |  | 2025-09-23 | Email your Sponsor with an update |  |  |  |  | 2025-11-02 |  | If you have a sponsor for this request, please send them an email with an update. Locate the Communications template document and use the Initial Sponsor Communication template as a starting point. |  | test2 | Finalize the criteria matrix template | Select 3-4 vendor platforms to do a quick vendor discovery
1211448483833103 | 2025-09-23 |  | 2025-09-23 | Select 3-4 vendor platforms to do a quick vendor discovery |  |  |  |  | 2025-11-04 |  | ** This task only applies if you are considering multiple software solutions and do not have one in mind, and you are looking for software that best meets your requirements. If you are looking to integrate data with Novi AMS, start by finding https://www.noviams.com/third-party-integrations. If vendor(s) are listed on their website, chances are they have a good relationship with Novi. To do further research on vendors, check out vendor Capterra reviews. |  | test2 | Email your Sponsor with an update | Email the project team to invite them to discovery sessions,Participate in vendor discovery calls
1211448483901468 | 2025-09-23 |  | 2025-09-23 | Email the project team to invite them to discovery sessions |  |  |  |  | 2025-11-06 |  | ** This task only applies if you are considering multiple software solutions and do not have one in mind, and you are looking for software that best meets your requirements. Please utilize the Communication template that you copied in the first task. Locate the Invite to Demos language and use it as a starting point. Invite any Directors, team leads, or Sponsors who wish to participate in the demos. |  | test2 | Select 3-4 vendor platforms to do a quick vendor discovery
1211448310082299 | 2025-09-23 |  | 2025-09-23 | Participate in vendor discovery calls |  |  |  | 2025-11-06 | 2025-11-12 |  |  |  | test2 | Select 3-4 vendor platforms to do a quick vendor discovery | Email vendors from Discovery you want to invite to RFI/RFP
1211448310082306 | 2025-09-23 |  | 2025-09-23 | Email vendors from Discovery you want to invite to RFI/RFP |  |  |  | 2025-11-07 | 2025-11-12 |  | ** This task only applies if you are considering multiple software solutions and do not have one in mind, and you are looking for software that best meets your requirements. Complete vendor demo forms, set up 60-minute demos, and obtain pricing. Record one-time pricing and ongoing costs in the Criteria matrix. RFI: Complete matrix and provide dates/times for extended 1 hour demo RFP: Copy https://citeorg-my.sharepoint.com/:w:/r/personal/laurel_nava_cite_org/Documents/Microsoft%20Teams%20Chat%20Files/CITE%20RFP%20Template.docx?d=w9bc13ef4ffb94d1a8244c25abd471fb0&csf=1&web=1&e=fjJJ0h, modify the copy, convert to PDF, save PDF in Google Drive, share RFP proposal you create using the template. Have vendor complete matrix and provide dates/times for extended 1 hour demo. |  | test2 | Participate in vendor discovery calls | Wait for vendor responses
1211448310082313 | 2025-09-23 |  | 2025-09-23 | Wait for vendor responses |  |  |  | 2025-11-13 | 2025-12-08 |  | ** This task only applies if you are considering multiple software solutions and do not have one in mind, and you are looking for software that best meets your requirements. This is a waiting period while we wait for responses from vendors. |  | test2 | Email vendors from Discovery you want to invite to RFI/RFP
1211448310460440 | 2025-09-23 |  | 2025-09-23 | Create a Criteria Matrix rubric for each vendor presentation and share with project team members |  |  |  |  | 2025-12-09 |  | ** This task only applies if you are considering multiple software solutions and do not have one in mind, and you are looking for software that best meets your requirements. Make a copy of the criteria matrix and create a tab for each vendor on your Criteria Matrix sheet. |  | test2 |  | Get platform selection buy-in from other teams
1211448310460447 | 2025-09-23 |  | 2025-09-23 | Participate in demos |  |  |  | 2025-12-21 | 2026-01-01 |  | ** This task only applies if you are considering multiple software solutions and do not have one in mind, and you are looking for software that best meets your requirements. Review matrix responses from Directors and project team members Send Directors and team members an email with matrix scores Inivite Directors and team members. As you meet with vendors during demos and share information about their platforms, evaluate the platforms using the criteria matrix. For each measurable criterion, score the platforms using the following scores: 4 - Meets requirement 3 - Almost meets requirement 2 - Somewhat meets requirement 1 - Does not meet requirement |  | test2
1211448309609047 | 2025-09-23 |  | 2025-09-23 | Get platform selection buy-in from other teams |  |  |  | 2026-01-02 | 2026-01-21 |  | The purpose of this task is to reiterate requirements, let everyone know about demos coming up, and encourage them to participate in the upcoming demos. |  | test2 | Create a Criteria Matrix rubric for each vendor presentation and share with project team members
1211448309609054 | 2025-09-23 |  | 2025-09-23 | Review matrix responses from Directors and project team members |  |  |  | 2026-01-02 | 2026-01-11 |  |  |  | Get platform selection buy-in from other teams
1211448309609061 | 2025-09-23 |  | 2025-09-23 | Send Directors and team members an email with matrix scores |  |  |  | 2026-01-11 | 2026-01-21 |  |  |  | Get platform selection buy-in from other teams
1211448310612302 | 2025-09-23 |  | 2025-09-23 | NOTE: Update the due date on this task! Email all vendors for thank them for their participation. Email one vendor to request a sandbox environment. |  |  |  |  | 2026-01-22 |  | The purpose of this task is to communicate the status of all vendors after the demos. For the one that is selected, ask for 2 references you can contact. |  | test2 |  | Test your requirements in Sandbox environment
1211448310692512 | 2025-09-23 |  | 2025-09-23 | Send rejections |  |  |  |  | 2026-01-22 |  | Thank the participants and inform them that we will not be moving forward. Please refer to the communication plan. |  | NOTE: Update the due date on this task! Email all vendors for thank them for their participation. Email one vendor to request a sandbox environment.
1211448310692519 | 2025-09-23 |  | 2025-09-23 | Send request for a sandbox |  |  |  |  | 2026-01-22 |  | Please send an email to request information from those under consideration. Refer to the communication plan. |  | NOTE: Update the due date on this task! Email all vendors for thank them for their participation. Email one vendor to request a sandbox environment.
1211448310612309 | 2025-09-23 |  | 2025-09-23 | Contact Vendor References and start chat with Marketing about integrations |  |  |  | 2026-01-23 | 2026-02-02 |  | At this stage, contact the vendor's references. Refer to the the Reference Check Questions sheet in Google Drive. |  | test2
1211448310612316 | 2025-09-23 |  | 2025-09-23 | Test your requirements in Sandbox environment |  |  |  | 2026-01-21 | 2026-02-10 |  | At this point, you have access to the sandbox environment. Please take the criteria list you created and test the functionality based on what you noted as "must-haves" and "nice-to-haves." This is a critical milestone. To move forward with the vendor, you must get buy-in from all of your stakeholders by the due date. |  | test2 | NOTE: Update the due date on this task! Email all vendors for thank them for their participation. Email one vendor to request a sandbox environment. | Review Contract for language
1211448250753202 | 2025-09-23 |  | 2025-09-23 | Send Directors and team members an email to participate in sandbox testing along with credentials |  |  |  | 2026-01-21 | 2026-02-10 |  |  |  | Test your requirements in Sandbox environment
1211448250753209 | 2025-09-23 |  | 2025-09-23 | Get final buy in or halt direction from Directors and team members |  |  |  | 2026-02-10 | 2026-02-20 |  | Please tag your stakeholders on this task and have them respond in the comments with either "Proceed" or "Halt." |  | Test your requirements in Sandbox environment
1211448310692498 | 2025-09-23 |  | 2025-09-23 | Review Contract for language |  |  |  | 2026-02-03 | 2026-02-15 |  | The purpose of this task is to ensure CITE is protected, CITE owns data, and that we are meeting state and federal regulations. Task is to be assigned to Andrea when this process goes for draft approval. |  | test2 | Test your requirements in Sandbox environment | Contract review period
1211448310692505 | 2025-09-23 |  | 2025-09-23 | Contract review period |  |  |  | 2026-01-01 | 2026-01-16 |  | Two week period for Andrea to review Contract language. |  | test2 | Review Contract for language
1211448251106130 | 2025-09-23 |  | 2025-09-23 | Email progress with Sponsor |  |  |  |  | 2026-02-17 |  | Share progress with the software selection. |  | test2 |  | Training with vendor
1211448251106137 | 2025-09-23 |  | 2025-09-23 | Training with vendor |  |  |  | 2026-02-18 | 2026-03-02 |  |  |  | test2 | Email progress with Sponsor | Implement selected software
1211448251106144 | 2025-09-23 |  | 2025-09-23 | Implement selected software |  |  |  | 2026-03-22 | 2026-04-11 |  | Period when we work with the vendor to implement software. |  | test2 | Training with vendor | Test your requirements in live environment
1211448310947656 | 2025-09-23 |  | 2025-09-23 | Migrate |  |  |  | 2026-02-17 | 2026-03-22 |  |  |  | Implement selected software
1211448310947663 | 2025-09-23 |  | 2025-09-23 | Integrate |  |  |  | 2026-02-17 | 2026-03-22 |  |  |  | Implement selected software
1211448251106151 | 2025-09-23 |  | 2025-09-23 | Test your requirements in live environment |  |  |  | 2026-04-11 | 2026-04-21 |  | Final criteria matrix test to ensure that the platform meets all requirements from all teams. |  | test2 | Implement selected software | Record and report software issues
1211448251181746 | 2025-09-23 |  | 2025-09-23 | Record and report software issues |  |  |  | 2026-04-11 | 2026-05-01 |  | Please go to the templates folder and find the, 'Record Changes or Issues' File. Record any issues and changes that you would like the vendor to make. |  | test2 | Test your requirements in live environment | Work with vendor to address issues
1211448311098495 | 2025-09-23 |  | 2025-09-23 | Work with vendor to address issues |  |  |  | 2026-04-11 | 2026-05-11 |  | Time the for vendor has to address issues. As defects or changes are addressed, update the, 'Record Change or Issues' file with updates. |  | test2 | Record and report software issues | Share new software news on Staff channel,Perform a Retrospective exercise
1211448311098502 | 2025-09-23 |  | 2025-09-23 | Share new software news on Staff channel |  |  |  |  | 2026-05-12 |  | Sharing news with other staff members for visibility and potential collaboration. |  | test2 | Work with vendor to address issues | Update CITE Software Excel spreadsheet
1211448311098509 | 2025-09-23 |  | 2025-09-23 | Update CITE Software Excel spreadsheet |  |  |  |  | 2026-05-13 |  | CITE maintains a single software sheet where we record all software requests. The purpose is to keep track of all the different software solutions selected, estimated costs, actual Total Cost of Ownership (TCO), status and for what year (Sokie). Location: https://citeorg.sharepoint.com/:x:/r/sites/Staff269/Shared%20Documents/Operational/Software%20Inventory.xlsx?d=w9a2dc28546374acb9858374ed0e59c39&csf=1&web=1&e=4DSrhy |  | test2 | Share new software news on Staff channel
1211448311098516 | 2025-09-23 |  | 2025-09-23 | Perform a Retrospective exercise |  |  |  |  | 2026-05-14 |  | The purpose of a retrospective is to look back at all of our work to see: what we did well, what we can improve, what we can get rid of, and what we can try in the future. Find the Retrospective file in the templates folder. After retrospective is complete, review notes and make improvements to the process in Asana or the original template files in https://drive.google.com/drive/folders/1IiqeBA5I3sITywwXlQYGOjM9xxg73KiI?usp=drive_link. |  | test2 | Work with vendor to address issues
1211448249779021 | 2025-09-23 |  | 2025-09-23 | Perform Impact Analysis |  |  |  |  | 2026-03-24 |  |  |  | Perform a Retrospective exercise
1209774309506205 | 2025-03-24 |  | 2025-05-21 | LMS Round 1 | Cancelled | Ailene Chang | Ailene.chang@cite.org |  |  |  | CONTACT INFO Project lead: Ailene Chang Email address: ailene.chang@cite.org Preferred method of communication? Email BACKGROUND Do you have an idea of what software you want to use? I have a need but I don't know what software options there are What is the name of software: Why is this necessary? Recertification process is overly complex and switching between programs and incredibly time-consuming for staff Current software doesn’t work, looks very patch and manual process Approval processes for activities is a very manual process Issuing badges is manual and not connected to Novi -In 2026, need a scalable solution. -New process should have lots of voices and buy-in -LMS needs to be focused on adult learning – Canvas isn’t really built for our needs --Students don’t have quick access to ed programs, recert, program sign ups, and CITE data in one place --Canvas is not connected to Novi which limits tracking and alumni upkeep -Ed team is hoping to integrate with Novi in a year or two…let’s get started on LMS selection now so this timeline is possible How will this help the problem? New approach allows us to standardize how we select software, improve our tracking mechanisms, and maximize the effectiveness of the systems we choose for our growing organization. What solution are you using at the moment? Canvas Do you need any reports? Yes. We need ability to track p prarticipant progress, grades, and recertification status. TIMELINE When do you need a solution in place? We need a solution preferrably with a start date of May 2026. Is there an urgency to find a software solution? The Canvas contract is set to expire September 2026. To account for migration, we need a few months in overlap for contracts, coordination (integration, migration, implementation, training, go live). COSTS How much does the software cost upfront? If you don't know, please give your best guess based on preliminary research. You can provide a range and/or justification for cost. Estimate a one time fee of around 12000 (startup fee and migration). Subscription fees? Yes How frequent are the fees? Yearly Monthly: Yearly: 9000 How much are we spending as an organization right now to address this need? For example: staffing, subscriptions, other fees. CONTRACTS Is this contract for multiple years? Yes How many years? 3 IMPACT & COMMUNICATIONS Who else needs to know about this software request? Laurel Nava - sponsor, Ty Ishimoto - Team Member, Rosie Talcott - Consultative, and Directors from other teams. Who will be using the software? Education Programs team and potentially Resource team What information will be shared and to whom? Selection and the Teams involved. REGULATIONS State or federal law requirements? To be discussed. Is data security required? yes INTEGRATIONS & MIGRATION Migration needed? yes, Canvas. Integration needed? yes, Novi. | Software Procurement Approval (SPA) Process |  |  |  | Project Path
1209775809047609 | 2025-03-24 | 2025-03-24 | 2025-03-24 | Please approve this purchase |  | Ailene Chang | Ailene.chang@cite.org |  | 2025-03-29 |  | https://app.asana.com/0/profile/1205692560497886 - Please review the responses on the form and approve/review/reject request. Then change assignee on the main task. Finally, move the main task along to a different section. |  | LMS Round 1
1209775923053740 | 2025-03-24 | 2025-03-24 | 2025-03-24 | Start here! |  | Ailene Chang | Ailene.chang@cite.org |  | 2025-01-07 |  | Your request has been reviewed by a member of the Exec team, and it has been determined that your request needs to go through an RFI or RFP process. What is a Request for Information (RFI)? Scenario: I have a need but I don't know what software options there are An RFI gathers information about potential vendors and their capabilities. Some RFIs mature into RFPs. Document used by organizations to gather information about potential vendors, products, or services before making a purchasing decision. It’s typically issued in the early stages of a project when the organization needs to understand the options available in the market and gain insight into vendor capabilities, offerings, and solutions. What is a Request for Proposal (RFP)? Scenarios: I want to explore a few options There are numerous competitors offering similar software services, with little differentiation between them; as a result, cost becomes the primary factor in decision-making. An RFP (Request for Proposal) is a formal document issued by an organization to solicit proposals from vendors or service providers. It outlines the organization's specific needs, objectives, and requirements for a particular project or service, and invites vendors to submit detailed proposals on how they can meet those needs. The RFP typically includes information such as the scope of work, budget, timeline, and evaluation criteria, and vendors respond with a proposal that explains their approach, qualifications, costs, and timeline for completing the project. The organization then reviews the proposals and selects the vendor that best meets its criteria. From an Asana perspective, you would follow the same predictive task path to acquire software. All of the tasks under this software request have been identified for you. Let's start by having you complete the subtasks in this task. Please review the tasks and the due dates. Move tasks to different dates as needed. Most of the tasks rely on the completion of previous tasks. In those cases, dates will recalculate to accommodate your date change(s). IMPORTANT NOTE: The 'select one solution to test' task is not reliant on a task dependency. Please make sure to update that specific task if you make changes to previous tasks before that one. Copy the templates from https://drive.google.com/drive/folders/1IiqeBA5I3sITywwXlQYGOjM9xxg73KiI?usp=drive_link to the Organization's Software Procurement folder. These documents are to be used at various points during the implementation and will help close out your processes. |  | LMS Round 1
1209775924472921 | 2025-03-24 | 2025-03-24 | 2025-03-24 | Review tasks and due dates |  | Ailene Chang | Ailene.chang@cite.org |  | 2025-01-07 |  |  |  | Start here! |  | Copy templates,Fill out planning document
1209775924472932 | 2025-03-24 | 2025-03-24 | 2025-03-24 | Copy templates |  | Ailene Chang | Ailene.chang@cite.org |  | 2025-01-07 |  |  |  | Start here! | Review tasks and due dates
1209775924399396 | 2025-03-24 | 2025-03-24 | 2025-03-24 | Fill out planning document |  | Ailene Chang | Ailene.chang@cite.org | 2025-01-08 | 2025-01-31 |  | This document outlines how a project will be executed, monitored, and controlled, including aspects like scope, schedule, budget, resources, and risk management. Review the planning document template. and complete it for your project. |  | LMS Round 1 | Review tasks and due dates | Align Director's schedules for 1:1 meetings
1209775924399407 | 2025-03-24 | 2025-03-24 | 2025-03-24 | Align Director's schedules for 1:1 meetings |  | Ailene Chang | Ailene.chang@cite.org |  | 2025-02-03 |  | Initiating a software request requires you to collaborate with all of the CITE subteam Directors to assess the impact on their teams. Align their schedules with yours to arrange Discovery meetings. |  | LMS Round 1 | Fill out planning document | Email individual meeting invites to each Director
1209775924399418 | 2025-03-24 | 2025-03-24 | 2025-05-08 | Email individual meeting invites to each Director |  | Ailene Chang | Ailene.chang@cite.org |  | 2025-02-04 |  | Please use the Communication template that you copied in the first task. Find the 'Communication for Directors Invite' section. There are two scenarios in the template. Scenario 1 is a meeting invite to share the software you have in mind and get feedback from the Director(s). Scenario 2 is a meeting with the Director(s) to gather requirements from their team. |  | LMS Round 1 | Align Director's schedules for 1:1 meetings | Meet with each Director and their team members
1209775924472910 | 2025-03-24 | 2025-03-24 | 2025-05-08 | Meet with each Director and their team members |  | Ailene Chang | Ailene.chang@cite.org | 2025-02-06 | 2025-02-20 |  | These sessions are meant to enhance transparency between teams and also make sure we account for everyone's input during this stage of the selection process. At this stage, we want to gather their requirements and gauge their interest in being involved in the process. It is important to emphasize the significance of reviewing tasks, meeting deadlines, and actively participating in the process. Additionally, we want to inform Directors that all communications regarding the project will be posted here, in Asana, and emailed so that everyone can see the communications. The following questions are part of the invite sent to Directors and what you will be asking each subteam to respond to: If software is known: Are you currently using any software similar to the one we are considering? If so, which software, and how are you utilizing it? Would your team be interested in using this software? If so, for what specific purposes? How would you use the solution? Are there any data or features from the solution that you believe would be beneficial for your team to access? If software is to be selected from a list of vendors: Are you currently using any software similar to the solution we are considering? If so, which software, and how are you using it? How would you use the solution? How does considering this software impact your operations? Do you see your team as potential users of this new software solution? After reviewing our requirements, are there any additional requirements you would like to include as we search for a solution? Are there specific data types or features that you believe would be valuable for your team to have access to? |  | LMS Round 1 | Email individual meeting invites to each Director | Conduct Ed Team impact assessment and requirements gatheringn meeting,Conduct Resource and Programs impact assessment and requirements gathering meeting,Conduct Marketing impact assessment and requirements gathering meeting,Document requirements from Director meetings to the Criteria Matrix,Conduct Exec team impact assessment and requirements gathering meeting
1209775924541045 | 2025-03-24 | 2025-03-25 | 2025-03-25 | Conduct Exec team impact assessment and requirements gathering meeting |  | Ailene Chang | Ailene.chang@cite.org |  | 2025-02-07 |  |  |  | Meet with each Director and their team members | Meet with each Director and their team members
1209775924576866 | 2025-03-24 | 2025-03-25 | 2025-03-25 | Conduct Ed Team impact assessment and requirements gatheringn meeting |  | Ailene Chang | Ailene.chang@cite.org |  | 2025-02-11 |  |  |  | Meet with each Director and their team members | Meet with each Director and their team members
1209775924576877 | 2025-03-24 | 2025-03-28 | 2025-03-28 | Conduct Resource and Programs impact assessment and requirements gathering meeting |  | Ailene Chang | Ailene.chang@cite.org |  | 2025-01-15 |  |  |  | Meet with each Director and their team members | Meet with each Director and their team members
1209775924644672 | 2025-03-24 | 2025-03-25 | 2025-03-25 | Conduct Marketing impact assessment and requirements gathering meeting |  | Ailene Chang | Ailene.chang@cite.org |  | 2025-02-12 |  |  |  | Meet with each Director and their team members | Meet with each Director and their team members
1209775819710753 | 2025-03-24 | 2025-03-24 | 2025-03-24 | Document requirements from Director meetings to the Criteria Matrix |  | Ailene Chang | Ailene.chang@cite.org | 2025-02-06 | 2025-02-20 |  | After meeting with each Director and the team members they invite, please add any additional criteria you've gathered into the Criteria Matrix Template located in the templates folder. If you know the software you want, it must meet the list of CITE criteria as well as the criteria that you and the Directors have identified as requirements. |  | LMS Round 1 | Meet with each Director and their team members | Email Criteria Matrix to Directors (or team leads) for feedback,Finalize the criteria matrix template
1209775819710764 | 2025-03-24 | 2025-03-24 | 2025-03-24 | Email Criteria Matrix to Directors (or team leads) for feedback |  | Ailene Chang | Ailene.chang@cite.org |  | 2025-02-21 |  | Locate the Communications template document you copied earlier. Find the Criteria Email to Director or Team Lead language and use it as a starting point. Send an email communication to the Directors to ensure that their requirements have been considered in the Criteria Matrix, which will be sent to vendors for their response. |  | LMS Round 1 | Document requirements from Director meetings to the Criteria Matrix
1209775819710775 | 2025-03-24 | 2025-03-24 | 2025-03-24 | Finalize the criteria matrix template |  | Ailene Chang | Ailene.chang@cite.org |  | 2025-02-24 |  | After receiving feedback from Directors and/or team leads, finalize the Criteria Matrix before sharing it with potential vendors. If you know the software you want, ensure that it meets all of the must-have requirements in the Criteria Matrix. |  | LMS Round 1 | Document requirements from Director meetings to the Criteria Matrix | Email your Sponsor with an update
1209775819829229 | 2025-03-24 | 2025-03-24 | 2025-03-24 | Email your Sponsor with an update |  | Ailene Chang | Ailene.chang@cite.org |  | 2025-02-26 |  | If you have a sponsor for this request, please send them an email with an update. Locate the Communications template document and use the Initial Sponsor Communication template as a starting point. |  | LMS Round 1 | Finalize the criteria matrix template | Select 3-4 vendor platforms to do a quick vendor discovery
1209775819829240 | 2025-03-24 | 2025-03-24 | 2025-03-24 | Select 3-4 vendor platforms to do a quick vendor discovery |  | Ailene Chang | Ailene.chang@cite.org |  | 2025-02-27 |  | ** This task only applies if you are considering multiple software solutions and do not have one in mind, and you are looking for software that best meets your requirements. If you are looking to integrate data with Novi AMS, start by finding https://www.noviams.com/third-party-integrations. If vendor(s) are listed on their website, chances are they have a good relationship with Novi. To do further research on vendors, check out vendor Capterra reviews. |  | LMS Round 1 | Email your Sponsor with an update | Email the project team to invite them to discovery sessions,Participate in vendor discovery calls
1209775924874385 | 2025-03-24 | 2025-03-24 | 2025-03-24 | Email the project team to invite them to discovery sessions |  | Ailene Chang | Ailene.chang@cite.org |  | 2025-03-03 |  | ** This task only applies if you are considering multiple software solutions and do not have one in mind, and you are looking for software that best meets your requirements. Please utilize the Communication template that you copied in the first task. Locate the Invite to Demos language and use it as a starting point. Invite any Directors, team leads, or Sponsors who wish to participate in the demos. |  | LMS Round 1 | Select 3-4 vendor platforms to do a quick vendor discovery
1209775924874396 | 2025-03-24 | 2025-03-24 | 2025-03-24 | Participate in vendor discovery calls |  | Ailene Chang | Ailene.chang@cite.org | 2025-03-03 | 2025-03-07 |  |  |  | LMS Round 1 | Select 3-4 vendor platforms to do a quick vendor discovery | Email vendors from Discovery you want to invite to RFI/RFP
1209775924874407 | 2025-03-24 | 2025-03-24 | 2025-03-24 | Email vendors from Discovery you want to invite to RFI/RFP |  | Ailene Chang | Ailene.chang@cite.org | 2025-03-07 | 2025-03-07 |  | ** This task only applies if you are considering multiple software solutions and do not have one in mind, and you are looking for software that best meets your requirements. Complete vendor demo forms, set up 60-minute demos, and obtain pricing. Record one-time pricing and ongoing costs in the Criteria matrix. RFI: Complete matrix and provide dates/times for extended 1 hour demo RFP: Copy https://citeorg-my.sharepoint.com/:w:/r/personal/laurel_nava_cite_org/Documents/Microsoft%20Teams%20Chat%20Files/CITE%20RFP%20Template.docx?d=w9bc13ef4ffb94d1a8244c25abd471fb0&csf=1&web=1&e=fjJJ0h, modify the copy, convert to PDF, save PDF in Google Drive, share RFP proposal you create using the template. Have vendor complete matrix and provide dates/times for extended 1 hour demo. |  | LMS Round 1 | Participate in vendor discovery calls | Wait for vendor responses,Send vendor demo invites and wait them to accept invites
1209775925211206 | 2025-03-24 | 2025-04-18 | 2025-04-18 | Wait for vendor responses |  | Ailene Chang | Ailene.chang@cite.org | 2025-04-03 | 2025-04-18 |  | ** This task only applies if you are considering multiple software solutions and do not have one in mind, and you are looking for software that best meets your requirements. This is a waiting period while we wait for responses from vendors. |  | LMS Round 1 | Email vendors from Discovery you want to invite to RFI/RFP
1209914458821625 | 2025-04-07 | 2025-04-25 | 2025-04-25 | Review vendor resopnses |  | Ailene Chang | Ailene.chang@cite.org | 2025-04-01 | 2025-04-18 |  |  |  | LMS Round 1
1209914458821627 | 2025-04-07 | 2025-04-21 | 2025-04-21 | Review MapleLMS responses |  | Ty Ishimoto | ty.ishimoto@cite.org |  | 2025-04-18 |  |  |  | Review vendor resopnses
1209914458821628 | 2025-04-07 | 2025-04-30 | 2025-04-30 | Review MobileMind responess |  | Ailene Chang | Ailene.chang@cite.org |  | 2025-04-18 |  |  |  | Review vendor resopnses
1209914458821629 | 2025-04-07 | 2025-04-18 | 2025-04-18 | Review Crowdwisdom responses |  | Ailene Chang | Ailene.chang@cite.org |  | 2025-04-18 |  |  |  | Review vendor resopnses
1209914458821634 | 2025-04-07 | 2025-04-22 | 2025-04-22 | Review Nextexams responses |  | Ailene Chang | Ailene.chang@cite.org |  | 2025-04-18 |  |  |  | Review vendor resopnses
1209775925211217 | 2025-03-24 | 2025-04-16 | 2025-04-16 | Send vendor demo invites and wait them to accept invites |  | Ailene Chang | Ailene.chang@cite.org | 2025-04-03 | 2025-04-15 |  | ** This task only applies if you are considering multiple software solutions and do not have one in mind, and you are looking for software that best meets your requirements. Vendor demos may be meetings that you can schedule with websites, or they may be arranged via email. |  | LMS Round 1 | Email vendors from Discovery you want to invite to RFI/RFP | Create a Criteria Matrix rubric for each vendor presentation and share with project team members,Participate in Demos
1209775819215908 | 2025-03-24 | 2025-04-18 | 2025-04-18 | Create a Criteria Matrix rubric for each vendor presentation and share with project team members |  | Ailene Chang | Ailene.chang@cite.org |  | 2025-04-17 |  | ** This task only applies if you are considering multiple software solutions and do not have one in mind, and you are looking for software that best meets your requirements. Make a copy of the criteria matrix and create a tab for each vendor on your Criteria Matrix sheet. |  | LMS Round 1 | Send vendor demo invites and wait them to accept invites | Participate in Demos
1210198044475911 | 2025-05-08 |  | 2025-05-21 | Get platform selection buy in from other teams |  | Ailene Chang | Ailene.chang@cite.org |  |  |  | The purpose of this task is reiterate requirements, let everyone know about demos coming up and encourage them to participate in the upcoming demos. |  | LMS Round 1
1210198044475920 | 2025-05-08 |  | 2025-05-08 | Marketing | [8 empty] | Get platform selection buy in from other teams
1210198044475917 | 2025-05-08 |  | 2025-05-08 | Resource and Programs | [8 empty] | Get platform selection buy in from other teams
1210198044475918 | 2025-05-08 |  | 2025-05-08 | Leadership | [8 empty] | Get platform selection buy in from other teams
1210198044475919 | 2025-05-08 |  | 2025-05-08 | EdPrograms | [8 empty] | Get platform selection buy in from other teams
1209775819215919 | 2025-03-24 | 2025-05-07 | 2025-05-21 | Participate in Demos |  | Ailene Chang | Ailene.chang@cite.org |  |  |  | ** This task only applies if you are considering multiple software solutions and do not have one in mind, and you are looking for software that best meets your requirements. As you meet with vendors during demos and share information about their platforms, evaluate the platforms using the criteria matrix. For each measurable criterion, score the platforms using the following scores: 4 - Meets requirement 3 - Almost meets requirement 2 - Somewhat meets requirement 1 - Does not meet requirement |  | LMS Round 1 | Create a Criteria Matrix rubric for each vendor presentation and share with project team members,Send vendor demo invites and wait them to accept invites
1209994082460740 | 2025-04-15 | 2025-04-30 | 2025-04-30 | MapleLMS - Test Badging and Certification/Recertification |  | Ty Ishimoto | ty.ishimoto@cite.org | 2025-04-15 | 2025-04-25 |  |  |  | Participate in Demos
1210198044475924 | 2025-05-08 |  | 2025-05-08 | Review matrix responses from Directors and project team members | [8 empty] | Participate in Demos
1210198044475925 | 2025-05-08 |  | 2025-05-08 | Send Directors and team members an email with matrix scores | [8 empty] | Participate in Demos
1209775820402240 | 2025-03-24 | 2025-05-07 | 2025-05-21 | NOTE: Update the due date on this task! Email all vendors for thank them for their participation. Email one vendor to request a sandbox environment. |  | Ailene Chang | Ailene.chang@cite.org |  |  |  | The purpose of this task is to communicate the status of all vendors after the demos. |  | LMS Round 1 |  | Test your requirements in Sandbox environment
1209775814706534 | 2025-03-24 |  | 2025-03-24 | Send rejections | [6 empty] | Thank the participants and inform them that we will not be moving forward. Please refer to the communication plan. |  | NOTE: Update the due date on this task! Email all vendors for thank them for their participation. Email one vendor to request a sandbox environment.
1209775820713434 | 2025-03-24 |  | 2025-05-08 | Send request for a sandbox | [6 empty] | Please send an email to request information from those under consideration. Refer to the communication plan. |  | NOTE: Update the due date on this task! Email all vendors for thank them for their participation. Email one vendor to request a sandbox environment.
1210086653052726 | 2025-04-25 | 2025-04-28 | 2025-04-28 | Review recommendation email with Ty |  | Ty Ishimoto | ty.ishimoto@cite.org |  | 2025-04-28 |  |  |  | NOTE: Update the due date on this task! Email all vendors for thank them for their participation. Email one vendor to request a sandbox environment.
1209812623634509 | 2025-03-27 | 2025-05-07 | 2025-05-21 | Contact Vendor References |  | Ailene Chang | Ailene.chang@cite.org |  |  |  | At this stage, contact the vendor's references. Fill in the the Reference Check Questions sheet in Google Drive. Feel free to add any others that apply to you. |  | LMS Round 1
1209775820455583 | 2025-03-24 |  | 2025-05-21 | Test your requirements in Sandbox environment |  | Ailene Chang | Ailene.chang@cite.org |  |  |  | At this point, you have access to the sandbox environment. Please take the criteria list you created and test the functionality based on what you noted as "must-haves" and "nice-to-haves." |  | LMS Round 1 | NOTE: Update the due date on this task! Email all vendors for thank them for their participation. Email one vendor to request a sandbox environment. | Review Contract for language
1210198044475929 | 2025-05-08 |  | 2025-05-08 | Send Directors and team members an email to participate in sandbox testing along with credentials | [8 empty] | Test your requirements in Sandbox environment
1210198044475930 | 2025-05-08 |  | 2025-05-08 | Get final buy in or halt direction from Directors and team members | [8 empty] | Test your requirements in Sandbox environment
1209775820455594 | 2025-03-24 |  | 2025-05-21 | Review Contract for language |  | Ailene Chang | Ailene.chang@cite.org |  |  |  | The purpose of this task is to ensure CITE is protected, CITE owns data, and that we are meeting state and federal regulations. Task is to be assigned to Andrea when this process goes for draft approval. |  | LMS Round 1 | Test your requirements in Sandbox environment | Contract review period
1209775820455605 | 2025-03-24 |  | 2025-05-21 | Contract review period |  | Ailene Chang | Ailene.chang@cite.org |  |  |  | Two week period for Andrea to review Contract language. |  | LMS Round 1 | Review Contract for language
1209775820753670 | 2025-03-24 |  | 2025-05-21 | Email progress with Sponsor |  | Ailene Chang | Ailene.chang@cite.org |  |  |  | Share progress with the software selection. |  | LMS Round 1 |  | Training with vendor
1209775820753681 | 2025-03-24 |  | 2025-05-21 | Training with vendor |  | Ailene Chang | Ailene.chang@cite.org | [5 empty] | LMS Round 1 | Email progress with Sponsor | Implement selected software,Migrate,Integrate
1209775820753692 | 2025-03-24 |  | 2025-05-21 | Implement selected software |  | Ailene Chang | Ailene.chang@cite.org |  |  |  | Period when we work with the vendor to implement software. |  | LMS Round 1 | Training with vendor | Test your requirements in live environment
1209786443619629 | 2025-03-25 |  | 2025-06-16 | Migrate |  | Ailene Chang | Ailene.chang@cite.org | [5 empty] | Implement selected software | Training with vendor
1209786443619630 | 2025-03-25 |  | 2025-06-16 | Integrate |  | Ailene Chang | Ailene.chang@cite.org | [5 empty] | Implement selected software | Training with vendor
1209775820813872 | 2025-03-24 |  | 2025-05-21 | Test your requirements in live environment |  | Ailene Chang | Ailene.chang@cite.org |  |  |  | Final criteria matrix test to ensure that the platform meets all requirements from all teams. |  | LMS Round 1 | Implement selected software | Record and report software issues
1209775820813883 | 2025-03-24 |  | 2025-05-21 | Record and report software issues |  | Ailene Chang | Ailene.chang@cite.org |  |  |  | Please go to the templates folder and find the, 'Record Changes or Issues' File. Record any issues and changes that you would like the vendor to make. |  | LMS Round 1 | Test your requirements in live environment | Work with vendor to address issues
1209775923729015 | 2025-03-24 |  | 2025-05-21 | Work with vendor to address issues |  | Ailene Chang | Ailene.chang@cite.org |  |  |  | Time the for vendor has to address issues. As defects or changes are addressed, update the, 'Record Change or Issues' file with updates. |  | LMS Round 1 | Record and report software issues | Share new software news on Staff channel,Perform a Retrospective exercise
1209775923729026 | 2025-03-24 |  | 2025-05-21 | Share new software news on Staff channel |  | Ailene Chang | Ailene.chang@cite.org |  |  |  | Sharing news with other staff members for visibility and potential collaboration. |  | LMS Round 1 | Work with vendor to address issues | Update CITE Software Excel spreadsheet
1209775926274820 | 2025-03-24 |  | 2025-05-21 | Update CITE Software Excel spreadsheet |  | Ailene Chang | Ailene.chang@cite.org |  |  |  | CITE maintains a single software sheet where we record all software requests. The purpose is to keep track of all the different software solutions selected, estimated costs, actual Total Cost of Ownership (TCO), status and for what year (Sokie). Location: https://citeorg.sharepoint.com/:x:/r/sites/Staff269/Shared%20Documents/Operational/Software%20Inventory.xlsx?d=w9a2dc28546374acb9858374ed0e59c39&csf=1&web=1&e=4DSrhy |  | LMS Round 1 | Share new software news on Staff channel
1209775926274831 | 2025-03-24 |  | 2025-05-21 | Perform a Retrospective exercise |  | Ailene Chang | Ailene.chang@cite.org |  |  |  | The purpose of a retrospective is to look back at all of our work to see: what we did well, what we can improve, what we can get rid of, and what we can try in the future. Find the Retrospective file in the templates folder. After retrospective is complete, review notes and make improvements to the process in Asana or the original template files in https://drive.google.com/drive/folders/1IiqeBA5I3sITywwXlQYGOjM9xxg73KiI?usp=drive_link. |  | LMS Round 1 | Work with vendor to address issues
1209775926367265 | 2025-03-24 | 2025-10-07 | 2025-10-07 | Perform Impact Analysis |  | Ailene Chang | Ailene.chang@cite.org |  | 2025-10-03 |  |  |  | Perform a Retrospective exercise