## Master Assigment
Last Updated: 3/13/2020 @ 11:38AM
ID | Assignment | Date Assigned | Target Date | Lead | Support | Category | Priority | Status | Next Action | Notes - History | SecureShare / Communication Name (include status)
A01 | Delegation of Authority | 2020-03-06 |  |  |  | Administrative | 2-Medium | In-progress
A02 | BCP Backups | 2020-03-09 | 2020-03-10 |  |  | Administrative | 2-Medium | In-progress
A03 | Quarentine Letter (in case its needed) | 2020-03-13 |  |  |  | Administrative | 2-Medium | Not started
B01 | Version Control Issues | 2020-03-09 |  |  |  | Administrative | 2-Medium | Complete
B02 | Confirm access to Secure Share | 2020-03-09 | 2020-03-12 |  |  | Administrative | 3-Low | Complete
B03 | Review Work at Home Best Practices | 2020-03-12 |  |  |  | Administrative | 3-Low | In-progress
C01 | Tailgate deck - detailed | 2020-03-06 | 2020-02-12 |  |  | Communications | 3-Low | In-progress
C02 | LMS training wave 1 | 2020-03-03 | 2020-03-13 |  |  | Leadership | 1-High | In-progress
C03 | LMS training wave 2 | 2020-03-02 | 2020-03-20 |  |  | Training | 2-Medium | In-progress
C04 | Clorox 360 Training | 2020-03-12 |  |  |  | Training | 2-Medium | Not started
D01 | Scrolling monitors | 2020-03-02 | 2020-03-03 |  |  | Communications | 3-Low | Complete
D02 | Management Script | 2020-03-07 |  |  |  | Communications | 2-Medium | Complete
D03 | Limit on Domestic Travel | 2020-03-06 |  |  |  | Communications | 2-Medium | Complete - Monitoring
D04 | Note to staff (re: IT daily, HIPPA, etc.) | 2020-03-07 |  |  |  | Communications | 2-Medium | Complete
D05 | Increased signage | 2020-03-02 | 2020-03-05 |  |  | Communications | 3-Low | Complete - Monitoring
D06 | Tips of the day changed to Tip by Text | 2020-03-02 | 2020-03-05 |  |  | Communications | 3-Low | Complete
D07 | Pop up signage | 2020-03-04 |  |  |  | Communications | 3-Low | In-progress
D08 | State Signage Displayed w/Command hook | 2020-03-05 |  |  |  | Communications | 3-Low | Complete
D09 | Third Party Vendors that employ contingent workers and consultants | 2020-03-05 |  |  |  | Legal / Communications | 2-Medium | Complete
D10 | Use of Bleach Memo | 2020-03-06 | 2020-03-07 |  |  | Communications | 2-Medium | Complete
D11 | Consolidate Communications | 2020-03-10 |  |  |  | Communications | 3-Low | In-progress
D12 | Use of Shift Change memos | 2020-03-06 | 2020-03-07 |  |  | Communications | 2-Medium | Complete
D13 | COVID Cyber Scams Awareness | 2020-03-10 |  |  |  | Communications | 2-Medium | Complete
D14 | Customer / Partner Communications | 2020-03-10 |  |  |  | Communications | 1-High | Complete
D15 | Café signage | 2020-03-11 |  |  |  | Communications | 2-Medium | Complete
D16 | IT Technical Communication / Package | 2020-03-11 |  |  |  | Communications | 1-High | Complete
D17 | Family Members | 2020-03-11 |  |  |  | Communications | 2-Medium | Complete
D18 | Work From Home Communication Strategy | 2020-03-11 |  |  |  | Communications | 2-Medium | Complete
D19 | Family Support Services | 2020-03-11 |  |  |  | Communications | 2-Medium | Complete
D20 | Memo to Staff on Taking Supplies | 2020-03-12 |  |  |  | Communications | 2-Medium | Complete
D21 | New Directive on Travel | 2020-03-12 |  |  |  | Communications | 1-High | Complete
D22 | Create Communications Chart | 2020-03-12 |  |  |  | Administrative | 2-Medium | Complete
D23 | Home mailings for Control Room Operators | 2020-03-12 |  |  |  | Leadership | 1-High | Complete
E01 | Virus data iSOC | 2020-03-04 | 2020-03-04 |  |  | Administrative | 3-Low | Complete
F01 | Returning Ret – Ops and Security | 2020-03-03 | 2020-03-05 |  |  | Workforce | 3-Low | In-progress
F02 | Labor leader discussion – 1st meet | 2020-03-03 | 2020-03-06 |  |  | Workforce | 3-Low | In-progress
F03 | Locked in pay policy | 2020-03-05 |  |  |  | Workforce | 3-Low | Complete
G01 | Control Room Hygiene Stations | 2020-03-02 | 2020-03-16 |  |  | Health & Safety | 1-High | Complete - Monitoring
G02 | Elevator Hygiene Stations | 2020-03-02 | 2020-03-16 |  |  | Health & Safety | 1-High | Complete
G03 | Conference Room Hygiene stations | 2020-03-02 | 2020-03-16 |  |  | Health & Safety | 1-High | In-progress
G04 | Procure non-contact thermometers | 2020-03-04 | 2020-03-06 |  |  | Leadership | 1-High | Complete
G05 | Procedure for Thermometer Usage | 2020-03-11 |  |  |  | Leadership | 1-High | In-progress
G06 | Administering Temperature Checks | 2020-03-11 |  |  |  | Leadership | 1-High | In-progress
H01 | Hygiene Supply Chain | 2020-03-03 | 2020-03-09 |  |  | Supply Chain | 1-High | In-progress
H02 | Industrial Supply Chain | 2020-03-03 | 2020-03-16 |  |  | Leadership | 1-High | In-progress
H03 | Major project risk | 2020-03-05 |  |  |  | Supply Chain | 2-Medium | In-progress
H04 | Food Supplies (MRES) on order | 2020-03-05 |  |  |  | Supply Chain | 1-High | Complete - Monitoring
H05 | Clorox 360 – WPO and sites | 2020-03-06 |  |  |  | Leadership | 1-High | In-progress
H06 | Major Project Monitoring | 2020-03-11 |  |  |  | Operations | 2-Medium | In-progress
I01 | Executive Management Committee Agenda | 2020-03-09 |  |  |  | Leadership | 1-High | Complete
I02 | Attendance report sites | 2020-03-11 |  |  |  | Leadership | 1-High | In-progress
I03 | Communication to leaders about no communication to NYPA All on Corona | 2020-03-06 |  |  |  | Communications | 1-High | Complete
I04 | ICS Structure | 2020-03-04 | 2020-03-06 |  |  | Leadership | 2-Medium | Complete
I05 | APPA Webinar on Best Practices | 2020-03-10 |  |  |  | Leadership | 3-Low | Not started
I06 | ESCC Coordination | 2020-03-11 |  |  |  | Communications | 3-Low | In-progress
I07 | Declaring Emergency | 2020-03-02 |  |  |  | Leadership | 1-High | Complete
J01 | Security Interviews/questioner | 2020-03-05 |  |  |  | Leadership | 1-High | In-progress
J02 | Security Incident Report | 2020-03-10 |  |  |  | Workforce | 1-High | Complete
J03 | Security Alarm Testing | 2020-03-10 |  |  |  | Operations | 3-Low | Complete
J04 | TruView Report Showing Addresses | 2020-03-10 |  |  |  | Administrative | 1-High | Complete
J05 | Meeting / Distribution List | 2020-03-11 |  |  |  | Administrative | 1-High | In-progress
J06 | ACS Changes to Restrict Access / Segregate Personnel | 2020-03-11 |  |  |  | Workforce | 2-Medium | Not started
J07 | NY.StateWatchCenter@dhses.ny.gov request | 2020-03-11 |  |  |  | Administrative | 1-High | Complete
J08 | List of A / B Groups and Personnel that must physically report to work | 2020-03-11 | 2020-03-11 |  |  | Leadership | 1-High | In-progress
K01 | Site Stage 2 cleaning (virus in Area) | 2020-03-05 |  |  |  | Health & Safety | 1-High | Complete - Monitoring
K02 | Company plane | 2020-03-06 |  |  |  | Health & Safety | 1-High | Complete - Monitoring
K03 | Site Stage 3 cleaning (virus in WPO) | 2020-03-05 |  |  |  | Health & Safety | 1-High | In-progress
K04 | Bleach – lift restrictions | 2020-03-04 |  |  |  | Health & Safety | 2-Medium | Complete
K05 | Shift turnover training | 2020-03-04 |  |  |  | Workforce | 2-Medium | Complete
K06 | Vehicle Cleaning | 2020-03-05 | 2020-03-06 |  |  | Health & Safety | 1-High | Complete - Monitoring
K07 | Social Distancing- no handshakes | 2020-03-05 |  |  |  | Communications | 2-Medium | Complete
K08 | Postponing large gatherings | 2020-03-05 |  |  |  | Communications | 2-Medium | Complete
K09 | Close Visitors Center (All sites) | 2020-03-05 |  |  |  | Leadership | 1-High | Monitoring
K10 | Westchester County Cluster Map & Radius | 2020-03-10 | 2020-03-10 |  |  | Leadership | 1-High | In-progress
K11 | Guidance for Positive Test Results (if needed) | 2020-03-11 |  |  |  | Leadership | 1-High | Complete - Monitoring
K12 | Nurses / medical practitioners | 2020-03-11 |  |  |  | Leadership | 1-High | In-progress
K13 | Office Closure Memo | 2020-03-12 |  |  |  | Communications | 2-Medium | In-progress
L01 | Canals Seasonal Workers | 2020-03-07 |  |  |  | Workforce | 3-Low | Monitoring
M01 | Shift Procedure | 2020-03-09 | 2020-03-09 |  |  | Leadership | 1-High | Complete - Monitoring
M02 | International Travel Suspended | 2020-03-02 | 2020-03-03 |  |  | Workforce | 1-High | Complete
M03 | Canals Museums | 2020-03-06 |  |  |  | Operations | 3-Low | In-progress
M04 | Pending Travel Review | 2020-03-03 | 2020-03-06 |  |  | Workforce | 1-High | In-progress
M05 | Designated POC for plants and sites to receive awareness materials / posters / etc. | 2020-03-06 |  |  |  | Workforce | 1-High | Complete
M06 | OEM / Transportation to Wads Worth Labs | 2020-03-06 |  |  |  | Governor's Office | 1-High | Complete
M07 | LPPC Response to Survey | 2020-03-06 |  |  |  | Administrative | 3-Low | Complete
M08 | Request for State Agency Medical Personnel | 2020-03-06 |  |  |  | Governor's Office | 1-High | Complete
M09 | NERC Alert Response | 2020-03-06 | 2020-03-12 |  |  | Administrative | 1-High | Complete
M10 | List of Janitorial Staff | 2020-03-09 |  |  |  | Operations | 2-Medium | In-progress
M11 | Contractor Travel to NYPA | 2020-03-09 |  |  |  | Leadership | 1-High | In-progress
M12 | OEM Driver Request | 2020-03-10 |  |  |  | Governor's Office | 1-High | In-progress
M13 | Intra-State Travel | 2020-03-10 |  |  |  | Leadership | 1-High | Complete - Monitoring
M14 | Assessing Operational Impacts | 2020-03-11 |  |  |  | Operations | 2-Medium | Not started
M15 | 500MW Outage in Late-March | 2020-03-12 |  |  |  | Operations | 1-High | In-progress
M16 | Script for Gil's Conference Calls with Operations | 2020-03-12 |  |  |  | Leadership | 1-High | Not started
N01 | Covid-19 questions email (for employees) | 2020-03-06 |  |  |  | Workforce | 2-Medium | In-progress
N02 | HR.services@nypa (for benefit questions) | 2020-03-07 |  |  |  | Workforce | 2-Medium | Complete
N03 | Employee Wellness Policy Stage 2 (Fitness for Duty themed) | 2020-03-03 | 2020-03-18 |  |  | Governance | 2-Medium | In-progress
N04 | Employee wellness policy stage 3 (Fitness for Duty themed) | 2020-03-03 | 2020-03-18 |  |  | Governance | 2-Medium | In-progress
N05 | FAQ Document | 2020-03-10 |  |  |  | Communications | 2-Medium | In-progress
N06 | FAQ Metrics | 2020-03-10 |  |  |  | Administrative | 2-Medium | Not started
N07 | New Employee Onboarding | 2020-03-13 |  |  |  | Workforce | 2-Medium | Not started
N08 | Back to work interview checklist | 2020-03-13 |  |  |  | Workforce | 2-Medium | Not started
O01 | Covid-19 Support | 2020-03-03 | 2020-03-05 |  |  | Workforce | 3-Low | Complete - Monitoring
O02 | Covid-19 daily report | 2020-03-02 |  |  |  | Leadership | 1-High | In-progress
O03 | Pandemic Monitoring Servers | 2020-03-11 |  |  |  | Operations | 2-Medium | Complete - Monitoring
O04 | AE2 Status | 2020-03-13 |  |  |  | Operations | 2-Medium | Not started
P01 | Covi-19 task force mail list | 2020-03-05 | 2020-03-05 |  |  | Administrative | 3-Low | Complete
P02 | NYPA All and Canals All Email address for distribution | 2020-03-07 |  |  |  | Administrative | 3-Low | Complete
P03 | Governor's Office request for mission critical personnel | 2020-03-09 | 2020-03-09 |  |  | Governor's Office | 1-High | Complete
P04 | Updates to Mission Essential / Work from Home Analysis | 2020-03-10 |  |  |  | Workforce | 3-Low | Deferred
Q01 | WBS code | 2020-03-02 | 2020-03-04 |  |  | Administrative | 3-Low | Complete
Q02 | H-0501 Coronavirus Diseases 2019 Emergency Preparedness and Related Expenditures | 2020-03-13 |  |  |  | Administrative | 2-Medium | In-progress
R01 | Work from home staff equipped | 2020-03-05 |  |  |  | Leadership | 1-High | In-progress
R02 | Work from home bandwidth | 2020-03-05 |  |  |  | Leadership | 1-High | In-progress
R03 | Create User Listserv | 2020-03-07 |  |  |  | Administrative | 3-Low | Complete
R04 | Equipment for Management Personnel | 2020-03-09 |  |  |  | Operations | 1-High | Complete
R05 | Priority Equipment | 2020-03-10 |  |  |  | Administrative | 1-High | Complete
R06 | Manager-All Distribution List | 2020-03-11 |  |  |  | Administrative | 2-Medium | Not started
S01 | Monitor new public health / NYS declarations | 2020-03-11 |  |  |  | Communications | 2-Medium | In-progress
S02 | Monitor Closures | 2020-03-11 |  |  |  | Administrative | 3-Low | In-progress
T01 | Field Personnel Safety | 2020-03-11 |  |  |  | Operations | 3-Low | Not started
T02 | Mutual Assistance | 2020-03-11 |  |  |  | Operations | 2-Medium | In-progress
T03 | Utility Ops and Visitor Centers | 2020-03-11 |  |  |  | Leadership | 1-High | In-progress
U01 | Sick Day Guidance | 2020-03-12 |  |  |  | Workforce | 2-Medium | In-progress
V01 | Key Customer Posture | 2020-03-11 |  |  |  | Finance | 3-Low | Not started
V02 | Operational Impact / Load Balancing | 2020-03-11 |  |  |  | Operations | 3-Low | Not started