## Cover Page
Quality Assurance Program |  | Rev 1.0
Project Name
Project ID
Project Manager
Quality Assurance Specialist
Project Summary
| Total Tests | Pass | Fail | N/A | %
Design QC | 50 | 0 | 0 | 0 | 0%
Engineering QC | 89 | 0 | 0 | 0 | 0%
Staging QC | 66 | 0 | 0 | 0 | 0%
Commissioning QC | 64 | 0 | 0 | 0 | 0%
Total | 269 | 0 | 0 | 0 | 0%
(This data auto-populates from the checklist tabs)
Quality Critical Path
Task | Responsibility | Due Date | Completion Date | Notes/Info |  | Progress Percent
Design Phase
QC: Design | ENG/ QA Specialist |  |  | Verify quality of design: Design Checklist
Engineering Phase
QC: Engineering | ENG/CAD/QA Specialist |  |  | Verify quality of engineering and CAD: Engineering Checklist
Staging Phase
Kickoff Meeting | PM |  |  | Pre-installation meeting checklist (not included in QA program)
Rack build/assembly/coding | Lead Tech/PGM |  |  | Staging Checklist to be completed for each rack
QC: Staging | PM/QA Spec/ENG |  |  | Verify quality of staged systems, racks, mockups: Staging Checklist
Install Phase
Arrival On-Site | Crew |  |  | Bring all equipment into site and check for all present
Arrival QC check | Lead Tech/PM |  |  | Unpack and inspect that there has been no damage in transit
Installation of Cabling & Devices | Lead Tech/Crew |  |  | Utilize daily and task level checklists
Turn On System | Lead Tech/Programmer |  |  | Equipment is installed and is powered up onsite to begin functional testing
System Calibration | Lead Tech |  |  | Display, DSP, AMPs, wireless freqs final setup
Verification | PM or Lead Tech |  |  | Commissioning Checklist
QC: Commissioning | PM/QA Spec/ENG |  |  | Verify quality of delivered system: Commissioning Checklist
UAT (User Acceptance Test) | Client/PM |  |  | Show client that all items of scope are functional
Training | Client/PM |  |  | Train the client or client represenatives how to use system
Customer Sign off | Client/PM |  |  | Installation is 100% and customer is satisfied
Items in RED are critical path Quality Assurance points.

## Design
Design Quality Assurance
# | Test Name | Description | Pass/Fail | Who does it? | Comments
Audio
1 | Audio Inputs | Verify adequate # of inputs (mixers, DSP, switchers, Matrix, Rapoport) for all mics, pgm sources + headroom
2 | Amp Power | Amplifer power and # channels selected to meet SOW & speaker type and quantity
3 | Speaker quantity | Quantity of speakers is appropriate for coverage areas
4 | Audio Control | Volume control and EQ methods addressed
5 | Install kits | Rack mount kits, wall mount kits, back boxes, accessories
6 | Color | Verify all device colors meet criteria (White, Black, Custom)
Video
7 | Display Size | Display sizes selected based on viewing application and distance of audience
8 | Aspect Ratio | Display aspect ratios, projectors match screens
9 | Video I/O | Signal I/Os checked for compatibility, verify adequate # of inputs and outputs + headroom
10 | Video transport | Signal distribution; amplification; transport; interfaceing is included. Check long cable runs.
11 | Compatibility | All signals checked for compatibility, transcoding, scaling, aspect ratio, & resolution?
12 | Lighting | Lighting control addressed? Offered?
13 | Blinds | Blinds control addressed? Offered?
14 | RP Design | Rear projection systems design verified and quotes obtained
15 | Lenses | Projector throw distances and appropriate lensing calculated
16 | Install kits | Mounts, kits, accessories and verified as compatible with devices and the architectural featrures of the project site
17 | Color | Verify all device colors meet criteria (White, Black, Custom)
Control
18 | Control Scope | Baseline functions of control system are defined in SOW
19 | Control I/O | Verify that adequate type and quantity of ports are included
20 | Power | Power supplies are included
21 | Network | IP Control functions (web, email, Fusion, RMS) defined and networking devices are included (switches, routers, WAPs)
Hardware
22 | Racks | Verify adequate quantity of racks and rack space for equipment
23 | Accessories | Major rack accessories are included
24 | Rack Power | AC power requirements completed, documented
25 | Power Distribution | Power protect, surge supress, regulated, switch/control
26 | Rack Cooling | BTU calc, cooling addressed? Venting and filtering? Fans?
27 | Plates | Custom wallplates design and cost estimated or quotes obtained
28 | Furniture | Custom furniture designed, quotes obtained
Estimates
29 | Materials | Estimates include cable footage, connectors, hardware, misc.
30 | Travel | Travel costs including time and expense
31 | Rentals | Equipment rentals, lifts, special tools, permitting, other costs
32 | Sub-contractors | Subcontract costs included (including travel related expenses)
33 | Permits and Fees | All fees including contract purchasing, permits, duties and tariffs, included?
34 | Labor | All labor tasks are reviewed and estimated based on Site Survey, known conditions, and devices and systems to be installed?
35 | Labor crosscheck | Labor to equip ratios checked, labor/labor category ratios verified
36 | Management Review | Management has supplied or reviewed and approved all labor, travel, parts and subs estimates
37 | SME Review | Any required SMEs have supplied or reviewed and approved any SME labor estimates
38 | Warranty | Warranty service is included
39 | Training | Training/adoption service is included
40 | Equip Pricing | Pricing check, registrations, special deals, discounts, etc.
41 | Freight | Check Freight estimates, free shipping exceptions, large items, expedite?
42 | Budget | Proposal meets client budget constraints?
43 | Registration | Sale opportunity registered with Manufacturers
44 | Tax | Verify correct sales tax rate for sales location
Scope
45 | SOW & BOM | Scope of Work is complete, and cross checked for accuracy with the BOM.
46 | Design | Basic design complies with SOW document/ user needs
47 | OFE | All OFE equipment identified by make, model, and age
48 | Sketches | Sketches Complete. Sketches match BOM, BOM matches Scope, Scope matches Sketches.
49 | Site Survey | Site Survey conducted and info verified against design
50 | Peer Review | PEER REVIEW: Project proposal, BOM, scope, site survey, sketch reviewed by second engineer
Design Quality Assurance Approval
| APPROVALS |  | DATE |  | COMMENTS
Designer
Signed:
QA Specialist
Signed:

## Engineering
Engineering Quality Assurance
# | Test Name | Description | Pass/Fail | Tools | Comments
Audio
1 | Coverage | Coverage patterns verified (EASE or ACAD Floorplans) (+/- dB)
2 | Speaker quantity | 70V speaker quantity determined from coverage area and overlap criteria
3 | RF Freqs | Check suitability of RF mic frequencies per region/city
4 | Volume Control | Volume control and EQ methods addressed
5 | # inputs | Verify adequate # of inputs for all mics, pgm sources
6 | Accessories | Mic cables, mic stands, mic clips, antennas, batteries, accys included?
7 | Amplifiers | Amplifers power and # channels selected to meet SOW
8 | Mounting | Speaker mounting accessories included in BOM
9 | Colors | Verify all device colors meet criteria
10 | S/N Ratio | S/N criteria defined and achieveable
Video
11 | Image Size | display sizes calculated for viewing application and distance of reader
12 | Contrast Ratio | Contrast level criteria defined and achievable
13 | Projection Throw | Projector throw distances and appropriate lensing calculated
14 | Rear Projection | Rear projection systems design verified and quotes obtained
15 | Lighting | Lighting control addressed?
16 | Blinds | Blinds control addressed?
17 | Resolution | Resolution and Aspect Ratio requirements met by all devices
18 | Signal I/O | Signal I/Os checked for compatibility
19 | Distribution | signal distribution; amplification; transport; interfaceing included?
20 | Interface | All signals been checked for compatibility?
21 | Mounting | All mounting accessories included and verified with architecural details
22 | Colors | Verify all device colors meet criteria
23 | Cables | All adapters and breakout cables itemized as equipment or PARTS
Control
24 | Program Review | A programmer has reviewed the entire design and verified control system components are correct.
25 | Power | Control system hardware power draw calculations verified, voltage drop calculated
26 | Ports | Port assignments for all controlled devices, ports allocated for all devices
27 | Functions Defined | Baseline function of control system is defined, Control GUI checklists are created
28 | Accessories | Additional devices (memory, engraving, batteries, switch) to meet scope of control
29 | Radio | RF Frequency coordination for 802.11A/B/G devices
30 | IP Control & Apps | E functions (web, email, remote monitoring, remote control) defined and coding time included
31 | Colors | Verify device colors meet criteria
Network, Servers, Software
32 | Network Topology | Networking cables, plates, relay racks, patch panels, closets, and drops designed, topology is defined
33 | Network switches, routers | All required switchers and routers, including OFE, are designed and shown in CAD
34 | Network Radio | All WAPs and other wireless transmission systems included, freqs coordinated
35 | Server Hardware | Server hardware configurations complete, servers are designated by primary use case, are located in CAD, and meet all min software requirements.
36 | Server OS and Applications | Server standard software including OS, anti-virus, Vmware, powershell, etc
37 | Server Software | Server applications required are defined, verified for accurate part number and software contract or maintainence plans
38 | IP Control & Apps | Planning is complete for interconnection and integration of network, servers, software, and devices.
39 | BYOD Applications | Software intended for BOYD (itunes, google play, etc.) is defined
Racks and Hardware
39 | Rack Space | Verify adequate rack space for equipment
40 | Rack Cooling | BTU calc complete, cooling addressed? Venting and filtering? Fans?
41 | Cable Mgmt | cable management parts estimated as materials.
42 | Mounting | All devices have mounting kits, ears, shelves, etc
43 | Depth | Rack depth verified for all equipment
44 | Colors | Verify device colors meet criteria
45 | Power Dist | Power protect, surge supress, regulated, switch/control
46 | Power Reqs | AC power requirements completed
47 | Accessories | Verify rack accessories included as equipment (tops, sides, rails, bases, casters, doors, chases, vents, blanks)
48 | Plates | Custom plates designed
49 | Furniture | Custom furniture designed
50 | Company ID Rack Plate | Verify included in rack elevation
51 | OFE/Others | ID OFE comm drops; networking, CATV, DSS, PSTN, ISDN requirements
Scope
52 | Design SOW review | Basic design complies with SOW document/ user needs
53 | Sync | CAD matches BOM, BOM matches Scope, Scope matches CAD.
54 | OFE | All OFE equipment identified by make, model, and age
55 | Survey | Site Survey conducted and info verified against design
56 | Peer Review | PEER REVIEW: Project proposal, BOM, scope, site survey, sketch reviewed by second engineer
CAD Design Check
57 | Signal Flow Validation | Verify complete AVC signal flow send and return paths for all devices
58 | Video & Display System | Verify Video systems components, switchers, mixers, processing, and extenders are included
59 | Video Signal Compatibility | Verify video signal compatibility from output to input, scalers are included as required
60 | Audio & Speakers System | Verify Audio systems components, switchers, mixers, processing, and extenders are included
61 | Audio Interface | Verify audio interconnect. Check balanced to unbalanced conversion. Verify no audio is Y together without combiners or passive summing devices.
62 | Speakers | Verify speaker tap levels on 70 volt systems are correct, speaker count and tap values supported by amps
63 | Control System | Verify Control system components, port assignments, interfaces, power supplies, and extenders are included
64 | Hardware System | Verify racks, furniture, lecterns, and carts are included with required accessories
65 | Digital Audio | Verify Cobranet, Dante or AVB system is complete with approved Ethernet Switches
66 | Data & POE System | Verify Data system (Ethernet) is complete and has Switch, Router and/or WAP provided as needed, POE verified
67 | Power system | Verify power distribution and grounding is per drawings, interfaces properly with any UPS, and there are enough outlets.
68 | Wireless | Verify wireless microphone, video, control and satellite antenna systems are engineered and included
69 | Cable and Connector Types | Verify correct cable types and connector types for all interconnects
70 | Cable Labels | Verify cable labeling, wire type, signal type, wire number; no duplicate cable numbers
71 | No Duplicates | Verify there are NO copy paste errors on equipment blocks, wire labels, and tags
72 | No Ommissions | Verify that all devices on drawings are included in BOM; all devices on BOM are depicted on drawings
73 | Scope Check | Verify the the CAD Package details and supports all the requirements listed in the Scope of Work
74 | Device locations | Verify location of equipment is noted on schematic, (rack vs. table, wall, ceiling, etc.)
75 | Design Review | Review design and Cad with Designer
CAD Standards Check
75 | CAD Package | CAD Package is complete, published in PDF format, and plotted as per Standards and Project Requirements
76 | Title Block | Verify all titleblock information is correct, including revisions, authors, customer info, and "not for contstruction" watermarks are removed upon approval
77 | Cover Page | TA-001 Cover page includes correct customer information, Whitlock Team, and sheet index
78 | Notes | TA-002 through TA-005 are included
79 | Planned Areas of Work | TA-101 On master floor plan, all areas of work are clearly noted and reference plan, section and elevation sheets with details
80 | Floor Plans | TA-100 Floor plans and Reflected Ceiling Plans indicate device locations, cable runs, power/conduit reqs, blocking reqs.
81 | Wall Elevations | TA-200 Elevations detail device mounting heights, project screen drops/limits, mounts, power outlets, conduit, boxes, backboxes, blocking, and coordination details for all AV devices.
82 | Wall Sections | TA-300 When required, these sheets indicate mounting details and requirements with Section views
83 | Large Scale Views | TA-400 When appropriate, these sheets indicate plan, RCP, elevation, and section details for individual rooms
84 | Connector Details | TA-500 sheets included showing pinouts for all termiantions required by project
85 | Device Mounting Details | TA-500 sheets included depeciting all devices to be mounted with specific moutning details
86 | System Schematics | TA-600 sheets included depicting all devices, interconnects, technical systems, and third party/OFE connections
87 | Plates | TA-700 Verify all input and output plates are depicted with correct connectors
88 | Racks, Furniture, Carts | TA-800 Verify rack elevations are complete, include power and heat mgmt., and include tables showing total power draw and BTU generation
89 | Storage | Digital file is saved and idenitifed in the Project Site Folder (Huddle site)
Engineering Quality Assurance Approval
| APPROVALS |  | DATE |  | COMMENTS
Designer
Signed:
QA Specialist
Signed:

## Staging
Staging Quality Assurance
# | Test Name | Description | Pass/Fail | Tools | Comments
Rack
1 | Clean | Verify that all devices and related surfaces are clean, polished, and free of temporary identifiers such as shipping stickers, Whitlock job numbers stickers, etc. |  | Cleaning supplies
2 | Accessories | All device accessories (remotes, adaptors, cables, etc) are collected and stored in a central location for delivery to customer. All equipment manuals are collected and given to the PM for final assembly of closeout docuemtation.
3 | Power | All devices are powered and grounded per the project specifications.
4 | Inventory Devices | Document a list of all equipment installed in the rack noting serial numbers. Affix printed stickers to the front and back of each device that indicate that devices serial number. |  | Serial number labels
5 | Device Labels | All switchers and devices with definable buttons are labeled on the devices. |  | Manufacturers labeling templates
6 | Document Settings | Document equipment settings, knob positions, and default settings on the devices (only after final setup is completed). (label the settings on the devices with arrows as needed) |  | flag or arrow stickers
7 | Inspect Cabling | Visual inspection of cabling: labeling, cable dress, signal separation, cable stress, serviceability, tie wraps not too tight (none on Cat 5). Cable labeling is positioned and oriented in a consistent manner, is legible and unambiguous.
8 | Inspect Connectors | Connector terminations are solid in their connectors, visually inspected, and in compliance with industry termination standards.
9 | Temperature | Thermal gradient inspected in racks; all equipment operating within manufacturers’ guidelines. Record temperature inside rack after being powered up for at least 1 hour. Mock up final installation conditions by covering racks with cardboard boxes as necessary. |  | Thermometer
10 | Safety | Verify no stray AC voltages on any equipment accessible to a user relative to ground, and no sharp or jagged surfaces accessible to a user. |  | Multi-Meter
11 | Photograph | Take digital photos of the front and rear of each completed rack. For large racks, 2 pictures are needed for top half and bottom half. |  | Camera
General
12 | Test | Power up and verify all devices are working properly and to manufactures specification. During Staging, at least 1 of every device must be tested for control, AV signals, and functionality.
13 | RMA | RMA all devices that do not work to manufacture's specifications, and document in issue tracking log
14 | Device Labels | All switchers and devices with definable buttons are labeled on the devices.
15 | CAD | Verify that CAD drawings are accurate, or are marked up with redlines to indicate any changes, Refer to CAD Checklist and verify its completion
Table top and portable Devices
16 | Test | Power and verify all devices are working properly and to manufactures specification |  | Cleaning supplies
17 | RMA | RMA all devices that do not work to manufacture's specifications, and document in issue tracking log
Setup and Configure Audio
18 | Speaker Setup | Speakers matching amp output, for 70V conenct one per zone/room for testing
19 | Mic Setup | Setup a min of 2 conferencing microphones including mute and indicator logic functions
20 | Audio DSP | Load all audio DSP site files, and configure audio gain structure appropriate for staging. Pre-EQ speakers
21 | Volume Controls | Verify that all volume controls work as expected, and the system starts up at a nominal and audible level |  | Signal Generator or portable playback device
22 | Stereo | Confirm that audio left goes to left program speaker, and audio right goes to right program speaker
23 | Audio Routing | Confirm that audio follows sources when selected, test all sources
24 | Equalization | Equalizers shall be adjusted for best intelligibility and uniform frequency response across the listener area |  | RTA
25 | Recording Levels | Test video and audio record levels on all recording decks and input to transmission systems
26 | Microphone Inputs | For audio conference systems, adjust microphone input gain so as to demonstrate that "standard talker", positioned at each talker position in the room, produces a 0 dBu level at the output of the output bus of the audio conference DSP device.
27 | Audio Mixers | Verify audio mixers (including DSPs and Soundboards) are setup and operating correctly. Load and test presets.
28 | Echo Cancellation | For conferencing systems, be able to demonstrate full duplex operation, with no reports of echo (as detected from the far end)
29 | Audio Test Calls | Make at least 3 test calls. Record sites called and results.
Setup and Configure Video
30 | Display setup | Verify optimum brightness, contrast, color temperature and color settings in all displays
31 | Projector Setup | Displays are focused, centered, and evenly illuminated with no geometric distortion
32 | Switcher Setup | Configure Matrix and/or Switchers, test all routing |  | Laptop
33 | HDMI & HDCP | Verify HDCP key exchange and handshaking between all devices. |  | Laptop and Video Test Generator
34 | Image Stability and Scaling | Display stable images, with no scaling-related visual artifacts when switching between, at a minimum,(1024 x 768@60, @70, @75), (1280 x 1024@60, @85), (1400x1050@60) (1600x1200@60) (1280 x 768@60), (1280 x 720@60) (HD 720p, 1080i, 1080p) sources, and/or all those specified in the performance criteria for this system. Record test results as pass/ fail, and certify that sources have been satisfactorily scaled to the native resolution by the digital display device. |  | Laptop and Video Test Generator
35 | Image Matching | When several displays are visible in a single space, demonstrate consistencies in displays using a NTSC bars with PLUGE signal to all. |  | Video Test Generator
36 | User inputs | Verify all user input plates, panels, table boxes, and hookup cables are working; test each input type |  | Laptop and Video Test Generator
37 | Video Sources | Verify all installed video sources (playback decks, cable boxes, set top boxes, cameras, computers, etc) display images when selected.
38 | Firmware | Verify that all devices in the video system have the correct firmware installed |  | Laptop
39 | Video Routing | Verify that video routing is correct per the user controls. |  | Laptop and Video Test Generator
40 | Video Scaling | Verify all video scalers are setup correctly and adjusted to meet project specs. |  | Laptop
41 | Video Processing | Verify all video processors, videowall processors, and/or multi-image processors are setup and configured as designed. |  | Laptop
42 | Camera setup | Verify camera image quality is acceptable.
43 | Camera Presets | Camera presets are programmed as specified
44 | Codec Options | Confirm that all codec options have been installed and are functional.
45 | Video Test calls | Make at least 3 test calls to Customer sites, using Customer Bridging or Conferences services. Record sites called and results. |  | VTC Network Drop
46 | Video Recording | Video record nonconformance's and anomalies.
Setup and Configure Control Systems
47 | Device Control | Verify that the control system has established consistent communication with all controlled devices, all APIs are correct, and device control is consistent after successive loss of power to the control system and/or controlled devices.
48 | Control | Configure all control devices, and load code
49 | Control | Complete control GUI checklist, and verify all button presses and functions pass. |  | Control GUI checklist
50 | Control Interfaces | Verify that all user interfaces such as touchpanels, button panels, web/browsers, are installed and working. Verify all button presses using the GUI Control checklist. |  | Control GUI checklist
51 | Wireless Control | All wireless devices tested for connectivity. Confirm no interference with other wireless systems. Confirm repeatable connectivity on dock/undock.
52 | Touchpanel Functionality | Verify all touchpanel controls, button presses, and logic functions using the Contorl GUI checklist
53 | Control latency | Touchpanel Page layouts, no more than 250ms latency on any button press
54 | Control Functions | The Control System performs all the functions with stability, and in sync with the equipment being controlled without the need to reset any item of equipment, and in conformance with the APPROVED touch panel flows
55 | Scheduled Events | Test and deactivate as necessary; all auto-sleep, auto-shutdown, or other "auto" device functions that are not required or that might interfere with expected control system functions
56 | Unexpected power loss & UPS Operation | Unexpected power loss test performed and passed, system restores to normal operation upon rebooting. If any user input is needed to restore functionality when the system powers up, those steps are documented and left with the rack. NOTE: DO NOT disconnect UPS service cords as this creates a dangerous un-grounded condition. Remove power from UPS at breaker panel to simulate outage. Verify UPS operation and adequate run time upon power loss.
57 | Occupancy Sensors | Verify that occupancy sensors are operating correctly and will not inadvertently shutdown the system when in use
58 | IP Control and monitoring | All e-controlled equipment properly configured with IP addresses, host names, time servers, Gatekeeper addresses, network configurations, as applicable.
Setup and Configure Network, Servers, and Software
59 | Network Topology | Networking cables, plates, relay racks, patch panels, closets, and drops designed, topology is defined
60 | Network switches, routers | All required switchers and routers, including OFE, are designed and shown in CAD
61 | Network Radio | All WAPs and other wireless transmission systems included, freqs coordinated
62 | Server Hardware | Server hardware configurations complete, servers are designated by primary use case, are located in CAD, and meet all minimum software requirements
63 | Server OS and Applications | Server standard software including OS, anti-virus, Vmware, powershell, etc
64 | Server Software | Server applications required are defined, verified for accurate part number and software contract or maintainence plans
65 | IP Control & Apps | Planning is complete for interconnection and integration of network, servers, software, and devices
66 | BYOD Applications | Software intended for BOYD (Itunes, google play, etc) is defined
Staging Quality Assurance Approval
| APPROVALS |  | DATE |  | COMMENTS
Staging Manager
Signed:
QA Specialist
Signed:

## Commissioning
Commissioning Quality Assurance
# | Test Name | Description | Pass/Fail | Tools | Comments
Pre-Requisites
1 | Design | Testing and QA complete and passed
2 | Engineering | Testing and QA complete and passed
3 | Staging | Testing and QA complete and passed
4 | Installation | Review all submitted Installation checklists and address any ourstanding issues
General
5 | Safety | Verify that all devices are installed in a safe manner, adhere to all mounting and installation instructions, and meeting all minimum safety requirements.
6 | Clean | Verify that all devices and related surfaces are clean, polished, and free of temporary identifiers such as shipping stickers, project job numbers stickers, etc. |  | Cleaning supplies
7 | Plumb and Level | All installed devices are plumb and level, free from visual defects and have not been adjusted or altered by others. |  | Laser Level
8 | Free of Damage | All installed devices are free of damage or visible defects.
9 | Accessories | All device accessories (remotes, adaptors, cables, etc) are collected and stored in a central location for delivery to customer. All equipment manuals are collected and given to the PM for final assembly of closeout docuemtation.
10 | Power | All devices are powered and grounded per the project specifications.
11 | Inventory Devices | Document a list of all equipment installed in the rack noting serial numbers. Affix printed stickers to the front and back of each device that indicate that devices serial number. |  | Serial number labels
12 | CAD | Current Redlines are available onsite, and a second set has been sent to CAD team to update all changes. Current redlines accurately reflect the as-built condidtion of all devices and systems. |  | CAD drawings
Commission Audio
13 | Speaker Setup | Speakers matching amp output, test and document 70V speaker impedance for each amplifier connection
14 | Mic Setup | Setup of all conferencing microphones including mute and indicator logic functions
15 | Audio DSP | Load all audio DSP site files, and configure audio gain structure appropriate for staging.
16 | Volume Controls | Verify that all volume controls work as expected, and the system starts up at a nominal and audible level |  | Signal Generator or portable playback device
17 | Stereo | Confirm that audio left goes to left program speaker, and audio right goes to right program speaker.
18 | Audio Routing | Confirm that audio follows sources when selected, test all sources.
19 | Equalization | Equalizers shall be adjusted for best intelligibility and uniform frequency response across the listener area. |  | RTA
20 | Recording Levels | Test video and audio record levels on all recording decks and input to transmission systems.
21 | Microphone Inputs | For audio conference systems, adjust microphone input gain so as to demonstrate that "standard talker", positioned at each talker position in the room, produces a 0 dBu level at the output of the output bus of the audio conference DSP device.
22 | Audio Mixers | Verify audio mixers (including DSPs and Soundboards) are setup and operating correctly. Load and test presets.
23 | Echo Cancellation | For conferencing systems, be able to demonstrate full duplex operation, with no reports of echo (as detected from the far end).
24 | Audio Test Calls | Make at least 3 test calls. Record sites called and results.
Commission Video
25 | Display setup | Verify optimum brightness, contrast, color temperature and color settings in all displays.
26 | Projector Setup | Displays are focused, centered, and evenly illuminated with no geometric distortion.
27 | Switcher Setup | Configure Matrix and/or Switchers, test all routing |  | Laptop
28 | HDMI & HDCP | Verify HDCP key exchange and handshaking between all devices. |  | Laptop and Video Test Generator
29 | Image Stability and Scaling | Display stable images, with no scaling-related visual artifacts when switching between, at a minimum,(1024 x 768@60, @70, @75), (1280 x 1024@60, @85), (1400x1050@60) (1600x1200@60) (1280 x 768@60), (1280 x 720@60) (HD 720p, 1080i, 1080p) sources, and/or all those specified in the performance criteria for this system. Record test results as pass/ fail, and certify that sources have been satisfactorily scaled to the native resolution by the digital display device. |  | Laptop and Video Test Generator
30 | Image Matching | When several displays are visible in a single space, demonstrate consistencies in displays using a NTSC bars with PLUGE signal to all. |  | Video Test Generator
31 | User inputs | Verify all user input plates, panels, table boxes, and hookup cables are working; test each input type |  | Laptop and Video Test Generator
32 | Video Sources | Verify all installed video sources (playback decks, cable boxes, set top boxes, cameras, computers, etc) display images when selected.
33 | Firmware | Verify that all devices in the video system have the correct firmware installed |  | Laptop
34 | Video Routing | Verify that video routing is correct per the user controls. |  | Laptop and Video Test Generator
35 | Video Scaling | Verify all video scalers are setup correctly and adjusted to meet project specs. |  | Laptop
36 | Video Processing | Verify all video processors, videowall processors, and/or multi-image processors are setup and configured as designed. |  | Laptop
37 | Camera setup | Verify each camera's image quality is acceptable.
38 | Camera Presets | Camera presets are programmed as specified
39 | Codec Options | Confirm that all codec options have been installed and are functional.
40 | Video Test calls | Make at least 3 test calls to Customer sites, using Customer Bridging or Conferences services. Record sites called and results. |  | VTC Network Drop
41 | Video Recording | Video record nonconformance's and anomalies.
Commission Control Systems
42 | Device Control | Verify that the control system has established consistent communication with all controlled devices, all APIs are correct, and device control is consistent after successive loss of power to the control system and/or controlled devices.
43 | Control | Configure all control devices, and load code
44 | Control | Complete control GUI checklist, and verify all button presses and functions pass. |  | Control GUI checklist
45 | Control Interfaces | Verify that all user interfaces such as touchpanels, button panels, web/browsers, are installed and working. Verify all button presses using the GUI Control checklist. |  | Control GUI checklist
46 | Wireless Control | All wireless devices tested for connectivity. Confirm no interference with other wireless systems. Confirm repeatable connectivity on dock/undock.
47 | Touchpanel Functionality | Verify all touchpanel controls, button presses, and logic functions using the Control GUI checklist.
48 | Control latency | Touchpanel Page layouts, no more than 250ms latency on any button press
49 | Control Functions | The Control System performs all the functions with stability, and in sync with the equipment being controlled without the need to reset any item of equipment, and in conformance with the APPROVED touch panel flows. |  | Approved Touchpanel Design
50 | Scheduled Events | Test and deactivate as necessary; all auto-sleep, auto-shutdown, or other "auto" device functions that are not required or that might interfere with expected control system functions.
51 | Unexpected power loss & UPS Operation | Unexpected power loss test performed and passed, system restores to normal operation upon rebooting. If any user input is needed to restore functionality when the system powers up, those steps are documented and left with the rack. NOTE: DO NOT disconnect UPS service cords as this creates a dangerous un-grounded condition. Remove power from UPS at breaker panel to simulate outage. Verify UPS operation and adequate run time upon power loss.
52 | Occupancy Sensors | Verify that occupancy sensors are operating correctly and will not inadvertently shutdown the system when in use.
53 | Divide and Combine rooms | Verify that all combinations work as designed.
54 | IP Control and monitoring | All e-controlled equipment properly configured with IP addresses, host names, time servers, Gatekeeper addresses, network configurations, as applicable.
Commission Network, Servers, and Software
55 | Network Topology | Networking cables, plates, relay racks, patch panels, closets, and drops designed, topology is defined
56 | Network switches, routers | All required switchers and routers, including OFE, are designed and shown in CAD
57 | Network Radio | All WAPs and other wireless transmission systems included, freqs coordinated
58 | Server Hardware | Server hardware configurations complete, servers are designated by primary use case, are located in CAD, and meet all min software requirements.
59 | Server OS and Applications | Server standard software including OS, anti-virus, Vmware, powershell, etc
60 | Server Software | Server applications required are defined, verified for accurate part number and software contract or maintainence plans
61 | IP Control & Apps | Planning is complete for interconnection and integration of network, servers, software, and devices.
62 | BYOD Applications | Software intended for BOYD (itunes, google play, etc) is defined.
Commissioning Quality Assurance Approval
I hereby certify that the system installed is complete, all items on the above checklist have been completed, that rack elevations are as specified, and that all engineering, fabrication, programming, installation, testing and checkout is complete and in accordance with the specification in product, practice, and performance, and that the system is ready to be placed into service.
| APPROVALS |  | DATE |  | COMMENTS
Senior Technician
Signed:
QA Specialist
Signed:

## Defaults
Metric | Value1 | Value2 | Value3 | Value4 | Value5
Version # | 1
Selection |  | Pass | Fail | N/A
design none | 55
design pass | 0
design fail | 0
design N/A | 0
engineering none | 98
engineering pass | 0
engineering fail | 0
engineering N/A | 0
staging none | 68
staging pass | 0
staging fail | 0
staging N/A | 0
commission none | 63
commission pass | 0
commission fail | 0
commission N/A | 0