## Instructions
The provided checklist is designed to assist the user with general installation guidance and pre-inspection quality control.
Refer to manufacturer's installation instructions for product specific information which may supercede the information given here.
See DrJ Best Practices for additional Educational Programs

## Checklist
Revised 2/15/2017
Items to be Checked | Installer | Building Official | Comments
Review Materials
Steel Angle - minimum 6” x 4” x 5/16”, full length of supporting roof section
Stops welded by others (if required)
Flashing
2x_ nailer to support sheathing of the adjacent roof
2x6 lumber reinforcement
16d nails
Veneer ties
Masonry
Wood Structural Sheathing
Other materials as specified by the Building Designer
Assembly Installation
2x_ nailer attached to support sheathing of the adjacent roof with 16d nails @ 12” o.c. scattered
Roof sheathing applied to nailer and adjacent roof trusses
2x6 lumber reinforcement installed parallel with steel shelf angle.
Steel angle attached as specified by the building designer
A 1” minimum clearance is present between the angle and lower roof deck to facilitate further roofing replacement and/or re-roofing
Counter flashing, step flashing, and weep holes are applied in the brick veneer wythe directly above the steel angle
Weep holes spaced a maximum of 33” o.c.
Veneer ties are attached at maximum 32” o.c. horizontally and 24” o.c. vertically to support a maximum of 2.67 sq ft of brick veneer wall area
Masonry veneer installed as specified
Vertical expansion joints present at a maximum of 25’ o.c.
Expansion joints sized between 3/8” and ½”, typical
Vertical expansion joints installed as appropriate at the following locations:
Corners
Offsets
Setbacks
Wall intersections
Changes in the wall height
Wall backing system changes
Brick veneer support changes
Wall function or climatic exposure changes